## Slide 1
NHS South Yorkshire
BAF, Risk Register and Issues Log – Rotherham Place Committee
16 April 2025
Appendix A

## Slide 2
This report is inclusive of: BAF Risks, Risks and Issues which are applicable to Rotherham Place Committee which have a residual score of 12 or above, whereby the Committee provides assurance. This report was presented at Rotherham PET on the 10 April 2025 The reporting period refers to 28 February 2025 – 4 April 2025

## Slide 3
STRATEGIC
OBJECTIVE
Principle
BAF & aligned
Risks
Changes
Executive
Actions
Risks Impacting on the System
Where the residual score is 12 or above
Board Assurance Framework
There are no current BAF Risks relating to Rotherham PET hat impact the system, that score above 12
Risk Register:
There are no current Risks relating to Rotherham PET that impact the system, that score above 12
Issues Log:
IL07 – R – Urgent Emergency Care – Score of 15
Following a review by Internal Audit the Corporate Risk Team have begun to update the digital BAF system. Gaps are now split into 2 different columns (in control and assurance).
Formal Executive Group – 19 March 2025
IL07 – R – SLE Performance Report
QPIE – 18 March 2025 IL07 – R – Urgent and Emergency Care Update
Supporting Papers

## Slide 4
STRATEGIC
OBJECTIVE
Principle
BAF & aligned
Risks
Changes
Executive
Actions
Objective 1: Improve Outcomes in Population Health and Healthcare
Where the residual score is 12 or above
Board Assurance Framework
There are no current issues relating to Rotherham PET under Objective 1, that score above 12
Risk Register:
SY021 – LEDER – Score of 12
SY040 – R – CAMHS – Score of 12
SY042 – R – Service Delivery – Score of 12
SY082 – Medical Emergency in Eating Disorders (MEED) – Score of 12
SY107 – R Community Paediatrics / Childrens Pathways – Score of 12
SY113 - Elective Care Waiting Times
SY124 – National Trajectory for Learning Disability and Autism (LDA) – Score of 16
Issues Log:
There are no current issues relating to Rotherham PET under Objective 1
Following a review by Internal Audit the Corporate Risk Team have begun to update the digital BAF system. Gaps are now split into 2 different columns (in control and assurance).
SY040 – R Risk description updated
SY107 – R – Risk owner changed
SY113 - Score reduced from 16 to 12, risk description and mitigation updated
Formal Executive Group – 19 March 2025
SY042 – R - Month 11 Financial Update
SY113 / SY124 SLE Performance Report
Rotherham Place Board – 19 March 2025
SY021 – LeDeR Lessons SY124 – Extracted Minutes re Learning Disabilities
QPIE – 18 March 2025 SY082 – Eating Disorders Programme
Finance and Investment Committee– 28 March 2025
SY042 – R- Financial Plan Update 25/26 Financial Update Month 11 Financial Update Appendix A Primary Care Capital Programme
Supporting Papers

## Slide 5
STRATEGIC
OBJECTIVE
Principle
BAF & aligned
Risks
Changes
Executive
Actions
Objective 2: Tackle Inequalities in Outcomes, Experience and Access
Where the residual score is 12 or above
Board Assurance Framework
There are no current issues relating to Rotherham PET under Objective 2, that score above 12
Risk Register:
SY082 – Medical Emergency in Eating Disorders (MEED) – Score of 12
SY113 - Elective Care Waiting Times
SY124 – National Trajectory for Learning Disability and Autism (LDA) – Score of 16
Issues Log:
IL07 – R – Urgent Emergency Care – Score of 15
IL17 – Continuing Health Care (CHC) – Score of 12
Following a review by Internal Audit the Corporate Risk Team have begun to update the digital BAF system. Gaps are now split into 2 different columns (in control and assurance).
SY113 - Score reduced from 16 to 12, risk description and mitigation updated
IL17 –mitigation updated
Formal Executive Group – 19 March 2025
SY113 / SY124 / IL07 – R – SLE Performance Report
QPIE – 18 March 2025 IL07 – R – Urgent and Emergency Care Update SY082 – Eating Disorders Programme
Rotherham Place Board – 19 March 2025 SY124 – Extracted Minutes re Learning Disabilities
Supporting Papers

## Slide 6
STRATEGIC
OBJECTIVE
Principle
BAF & aligned
Risks
Changes
Executive
Actions
Objective 3: Enhance Productivity and Value for Money
Where the residual score is 12 or above
Board Assurance Framework
There are no current BAF Risks relating to Rotherham PET under Objective 3, that score above 12
Risk Register:
SY124 – National Trajectory for Learning Disability and Autism (LDA) – Score of 16
Issues Log:
There are no current issues relating to Rotherham PET under Objective 3, that score above 12
Following a review by Internal Audit the Corporate Risk Team have begun to update the digital BAF system. Gaps are now split into 2 different columns (in control and assurance).
Formal Executive Group – 19 March 2025
SY124 SLE Performance Report
Rotherham Place Board – 19 March 2025 SY124 – Extracted Minutes re Learning Disabilities
Supporting Papers

## Slide 7
STRATEGIC
OBJECTIVE
Principle
BAF & aligned
Risks
Changes
Executive
Actions
Objective 4: Help the NHS Support Broader Social and Economic Value
Where the residual score is 12 or above
Board Assurance Framework
There are no current issues relating to Rotherham Place Board under Objective 4, that score above 12
Risk Register:
SY042 – R Service Delivery Score of 12
SY124 – National Trajectory for Learning Disability and Autism (LDA) – Score of 16
Issues Log:
There are no current issues relating to Rotherham Place Board under Objective 4
Following a review by Internal Audit the Corporate Risk Team have begun to update the digital BAF system. Gaps are now split into 2 different columns (in control and assurance).
Formal Executive Group – 19 March 2025
SY042 – R - Month 11 Financial Update
SY124 SLE Performance Report
Rotherham Place Board – 19 March 2025 SY124 – Extracted Minutes re Learning Disabilities
Finance and Investment Committee– 28 March 2025
SY042 – R- Financial Plan Update 25/26 Financial Update Month 11 Financial Update Appendix A Primary Care Capital Programme
Supporting Papers