## 1. Cover Sheet
Board Assurance Framework, Corporate Risk Register & Corporate Issues Log
Version : | Live
Meeting Date: | 2024-12-18
REPORT FOR: | Rotherham Place Board

## 2. Introduction
This document combines the Board Assurance Framework (BAF), the Risk Register and Issues Log for ease of access. Each section includes a cover sheet, open items, closed items and a change tracker. The document also includes the Risk Scoring Matrix and RACI model defines whether the people involved in the project will be Responsible, Accountable, Consulted and Informed. The document also features the Organogram to inform which committee is responsible for each risk. BAF objectives, Risks and Issues will be filtered to show those specific to the meeting in which the document is undergoing discussion / deep dive. Please can we request that any changes are highlighted in a different colour, and that any items for removal are only completed by Ruth Nutbrown, Alison Hague or Abby Sharp. In order to navigate the document, please find a contents list below; Tab 3 – Risk Scoring Matrix and RACI Board Assurance Frame Work (BAF) Tab 4 – Cover sheet Tab 5 – Open BAF - **key document** Tab 6 – Removed BAF Tab 7 – BAF Change Tracking Tab 8 – Organogram Risk Register Tab 9 – Cover sheet Tab 10 – Open Risks **key document** Tab 11 – Removed Risks Tab 12 – RR Change Tracking Issues Log Tab 13 – Cover sheet Tab 14 – Issues Log Tab 15 – Removed Issues Tab 16 – IL Change Tracking Place Partnerships Tab 17 – Cover sheet Tab 18 – Barnsley Place Partnership Tab 19 – Barnsley Place Partnership - Removed Risk Tab 20 – Barnsley Place Partnership - change tracking Tab 21 – Doncaster Place Partnership Tab 22– Doncaster Place Partnership - Removed Risk Tab 23 – Doncaster Place Partnership - change tracking Tab 24 – Rotherham Place Partnership Tab 25– Rotherham Place Partnership - Removed Risk Tab 26 – Rotherham Place Partnership - change tracking Tab 27 – Sheffield Place Partnership Tab 28– Sheffield Place Partnership - Removed Risk Tab 29 – Sheffield Place Partnership - change tracking The final, unnumbered, tab ‘list’ is for administrative purposes only. Please do not amend this section.

## 3. Risk Matrix Domain & RACI
Risk Scoring Matrix
Consequences / Severity
| Insignificant 1 | Minor 2 | Moderate 3 | Major 4 | Catastrophic 5
Likelihood
Rare 1 | 1 | 2 | 3 | 4 | 5
Unlikely 2 | 2 | 4 | 6 | 8 | 10
Possible 3 | 3 | 6 | 9 | 12 | 15
Likely 4 | 4 | 8 | 12 | 16 | 20
Almost Certain 5 | 5 | 10 | 15 | 20 | 25
| Low | Medium | High | Very High | Extreme
| 1-3 | 4-6 | 8-12 | 15-20 | 25
Review Frequency | Annually | Six Monthly | Quarterly | Monthly | Weekly
Table 1 Consequence Score (C)
Domains | Consequence score (severity levels) and examples of descriptors
| 1 | 2 | 3 | 4 | 5
| Insignificant | Minor | Moderate | Major | Catastrophic
Impact on the safety of patients, staff or public (physical/psychological harm) | Minimal injury requiring no/minimal intervention or treatment. No time off work | Minor injury or illness requiring minor intervention. Requiring time off work for > 3 days. Increase in length of hospital stay by 1-3 days | Moderate injury requiring professional intervention. Requiring time off work for 4-14 days. Increase in length of hospital stay by 4-15 days. RIDDOR/agency reportable incident. An event which impacts on a small number of patients | Major injury leading to long-term incapacity/disability. Requiring time off work for > 14 days. Increase in length of hospital stay by > 15 days. Mismanagement of patient care with long-term effects. | Incident leading to death. Multiple permanent injuries or irreversible health effects. An event which impacts on a large number of patients.
Quality/complaints/audit | Peripheral element of treatment or service suboptimal Informal complaint/inquiry | Overall treatment or service suboptimal Formal complaint (stage 1) Local resolution Single failure to meet internal standards Minor implications for patient safety if unresolved Reduced performance rating if unresolved | Treatment or service has significantly reduced effectiveness Formal complaint (stage 2) complaint Local resolution (with potential to go to independent review) Repeated failure to meet internal standards Major patient safety implications if findings are not acted on | Non-compliance with national standards with significant risk to patients if unresolved Multiple complaints/ independent review Low performance rating Critical report | Totally unacceptable level or quality of treatment/service Gross failure of patient safety if findings not acted on Inquest/ombudsman inquiry Gross failure to meet national standards
Human resources/ organisational development/staffing/ competence | Short-term low staffing level that temporarily reduces service quality (< 1 day) | Low staffing level that reduces the service quality | Late delivery of key objective/ service due to lack of staff Unsafe staffing level or competence (>1 day) Low staff morale Poor staff attendance for mandatory/key training | Uncertain delivery of key objective/service due to lack of staff Unsafe staffing level or competence (>5 days) Loss of key staff Very low staff morale No staff attending mandatory/ key training | Non-delivery of key objective/service due to lack of staff Ongoing unsafe staffing levels or competence Loss of several key staff No staff attending mandatory training /key training on an ongoing basis
Statutory duty/ inspections | No or minimal impact or breech of guidance/ statutory duty | Breech of statutory legislation Reduced performance rating if unresolved | Single breech in statutory duty Challenging external recommendations/ improvement notice | Enforcement action Multiple breeches in statutory duty Improvement notices Low performance rating Critical report | Multiple breeches in statutory duty Prosecution Complete systems change required Zero performance rating Severely critical report
Adverse publicity/ reputation | Rumours Potential for public concern | Local media coverage – short-term reduction in public confidence Elements of public expectation not being met | Local media coverage – long-term reduction in public confidence | National media coverage with <3 days service well below reasonable public expectation | National media coverage with >3 days service well below reasonable public expectation. MP concerned (questions in the House) Total loss of public confidence
Business objectives/ projects | Insignificant cost increase/ schedule slippage | <5 per cent over project budget Schedule slippage | 5–10 per cent over project budget Schedule slippage | Non-compliance with national 10–25 per cent over project budget Schedule slippage Key objectives not met | Incident leading >25 per cent over project budget Schedule slippage Key objectives not met
Finance including claims | Small loss Risk of claim remote | Loss of 0.1–0.25 per cent of budget Claim less than £10,000 | Loss of 0.25–0.5 per cent of budget Claim(s) between £10,000 and £100,000 | Uncertain delivery of key objective/Loss of 0.5–1.0 per cent of budget Claim(s) between £100,000 and £1 million Purchasers failing to pay on time | Non-delivery of key objective/ Loss of >1 per cent of budget Failure to meet specification/ slippage Loss of contract / payment by results Claim(s) >£1 million
Service/business interruption Environmental impact | Loss/interruption of >1 hour Minimal or no impact on the environment | Loss/interruption of >8 hours Minor impact on environment | Loss/interruption of >1 day Moderate impact on environment | Loss/interruption of >1 week Major impact on environment | Permanent loss of service or facility Catastrophic impact on environment
Table 2 Likelihood Score (L)
Likelihood Score
| 1 | 2 | 3 | 4 | 5
Descriptor | Insignificant | Minor | Moderate | Major | Catastrophic
Frequency How often might it/does it happen | This will probably never happen/recur | Do not expect it to happen/recur but it is possible it may do so | Might happen or recur occasionally | Will probably happen/recur but it is not a persisting issue | Will undoubtedly happen/recur, possibly frequently
RACI Model |  |  |  |  | Domains
Who is responsible for implementation | Who is accountable for the task completion | Who is consulted during process | Who should be informed when project complete
Glossary of Terms
Term | Definition
Action | The process and steps undertaken to achieve an aim
Assurance | Mechanisms we have in place to test the controls
Assurance Level | A measure of the strength / authentication mechanism and therefore the confidence in it. Assessed as 'low', 'medium' or 'high'
Cause of Risk | This is a description of why something could go wrong
Control | Controls in place to manage the risk; these are the actions that can be taken to manage or eliminate risk
Gaps in Control | Actions that have not been undertaken
Impact of Risk | The the consequence should the risk occur
Mitigating Actions | Actions we need to take, or mechanisms we need to put in place
Domains
1. Adverse publicity/ reputation
2. Business Objectives/ Projects
3. Finance including claims
4. Human Resources/ Organisational Development/ Staffing/ Competence
5. Impact on the safety of patients, staff or public (phys/psych)
6. Quality/ Complaints/ Audit
7. Service/Business Interruption/ Environmental Impact
8. Statutory Duties/ Inspections

## 3a. Heat Map
Updated - 07.06.24
BAF | Consequences / Severity
| Insignificant 1 | Minor 2 | Moderate 3 | Major 4 | Catastrophic 5
Likelihood
Rare 1
Unlikely 2 | 2.2, 2.4, 4.13.1, 4.13.2 | 2.3.1, 2.6 | 1.4.1, 1.6.3, 1.9.2, 1.10, 3.6 | 2.1.
Possible 3 | 3.1 | 3.4, 4.6, 4.12 | 1.1, 1.1.1, 1.2, 1.3, 1.7, 2.5, 2.9, 3.5 | 2.13 | 0.1.2
Likely 4 |  |  | 3.9 |  | 0.1.1, 4.3
Almost Certain 5 |  |  |  |  | 0.2
CORPORATE RISK REGISTER | Consequences / Severity
| Insignificant 1 | Minor 2 | Moderate 3 | Major 4 | Catastrophic 5
Likelihood
Rare 1
Unlikely 2 |  | SY106, SY125 | SY079, SY107, SY130
Possible 3 | SY004, SY017 | SY019, SY049, SY062, SY078, SY103 | SY006, SY016, SY044, SY082, SY112 | SY021, SY108, SY113, SY123 | SY131
Likely 4 | SY011 |  | SY040, SY061, SY063, SY066, SY069, SY091, SY107 | SY028, SY115, SY116, SY117, SY124, SY128, SY132 | SY042
Almost Certain 5
ISSUES LOG | Consequences / Severity
| Insignificant 1 | Minor 2 | Moderate 3 | Major 4 | Catastrophic 5
Likelihood
Rare 1
Unlikely 2
Possible 3 |  |  |  |  | IL07, IL08, IL09, IL20
Likely 4 |  |  | IL19 | IL17
Almost Certain 5 |  |  |  | IL03, IL12, IL13 | IL18

## 5(iiI) Rotherham BAF
|  | Accountable Officers | [5 empty] | 1st Line of Defence - Risk Ownership/ Front Line | 2nd Line of Defence - Risk Management' Corporate Oversight Functions | 3rd Line of Defence - External and internal audit, CIC Regulator, CQC, Monitor. |  | Control/Assurance Gap
Ref | How is the Board Assured that |  | Delegated to | Principal Oversight Committees that must be in the Governance Structure (Board, Sub-committee, Place Committee, SLE, QSG) | RACI | Source of Risk | Link to Risk Register/Issues Log | e.g. operational processes, project risk and control activity, business level monitoring | e.g. Finance, IT, Business Support, HR and Payroll | e.g. Monitor compliance and provide independent challenge and assurance | Risk Appetite | What additional actions need to be taken to manage this risk (including timescales) or what additional assurance do we need to seek. | What would be required to reduce the risk? | Residual Score | Assurance Level | Rationale for assurance level | ACTIONS | Progress/ Updates | Potential audit area | Date Reviewed | Due for Review | Review Frequency | Days Overdue | Pending Futher Details as at 30/10/24
[8 empty] | CONTROLS | INTERNAL ASSURANCE | EXTERNAL ASSURANCE | Initial Risk Score | [5 empty] | SMART (Specific, Measurable, Achievable, Resourced and Timely),
Objective 1: Improve Outcomes in Population Health and Healthcare - Executive Leads - Chief Medical Officer/Chief Nurse | [10 empty] | Risk Appetite 9 |  |  | Risk Appetite 9
1.1.1 - R | the ICB is maintaining quality, services and outcomes through Improvement and transformation | Chris Edwards Rotherham Place Director | Claire Smith | Quality Performance Patient Involvement Experience (QPPIE) Supported by SY ICB Place Committees | Accountable | South Yorkshire Joint Forward Plan | SY115, SY116, SY117, SY124, SY028, SY082, SY107, SY040, SY066, SY127, SY128, IL12, IL13, IL07, IL08, IL19, IL20 | 1)Rotherham Health and Care Place Plan details plans and is overseen by the Rotherham place board and the Health and Wellbeing board - Plan is also signed off by all statutory partners, VAR and Connect Healthcare. 2) Discussion are taking place sept/Oct 25 regarding new arrangements post ICB model changes and a review of the Plan to reflect new priorities and changing role of ICB. | 1) Rotherham Place Board receives monthly performance and quality reports. 2) Rotherham place leadership team meets weekly. 3) Place plan is being revised to align with revision of Health and Wellbeing board by May 25, engagement underway - will align to new planning guidance. | 1) Quarterly performance meetings between Rotherham place and SYICB. 2) RMBC health Select committee engage on issues as appropriate | 3 x 3 = 9 | none identified | The Rotherham Place Plan focuses on prevention and health inequalities so it needs to implemented over the next 2 years - what is the gap, has the plan not been implemented? | Robust governance is in place. Resource (workforce across partnership) to deliver all actions within our Place Plan and Population Health and Inequalities strategy is needed to deliver | 2 x 3 = 6 | Medium | Alongside the Place Plan there is a strategy and action plan formalised through the population health and inequalities steering group chaired by the Director of Public Health and Deputy Place Director ICB. Assurance on the action plan is via the steering group, Health and Wellbeing Board and Place Board. The plan is being revised alongside strategy (Place Plan). | 1) Implement Rotherham Health and Care plan. ensure that EQIAs are completed for all decisions - those relating to how we achieve efficiencies required. These will be done in year to March 26 2) Work with SY and Place partners on Deloitte's work to ensure that at Place we are have a robust transformation programme that supports demand management/quality provision by end of 2026. 3) Work with partners to understand how Place arrangements could be maintained in a new landscape given changes to ICBs by January 2026 | 0 | Delegated direct commissioning | 07/10/2024 11/11/2024 16/12/2024 06/01/2025 03/03/2025 04/04/2025 06/05/2025 10/06/2025 14/07/2025 18/08/2025 21/08/2025 22/09/2025 | 46103 | Six-Monthly | Not overdue
1.3 - R | The local healthcare system is sustainable, accessible and reactive to change, through the development and implementation of effective Local Place Partnerships and Plans. | Chris Edwards Rotherham Place Director | Claire Smith | Place Committee System Leaders Executive | Accountable | South Yorkshire Joint Forward Plan / BAF 2023 | SY082, SY028, SY069, SY040 | 1) Development and implementation of effective system-wide and Place Operational Plans 2) Effective delivery management processes at place including internal ICB escalation 3) Effective and responsive complaints and enquiries processes 4) Patient experience and engagement process 5) Integrated Care Strategy 6) 5 year ICB Plan 7) EPRR 8) NHS England/SY ICB Assurance MOU | 1) ICB Place Committees 2) Operational Executive 3) Board Sub Committee review | 1) Local Health and Welbeing Boards 2) NHSE Single Oversight Framework 3) NHSE Assurance process | 3 x 4 = 12 | none identified | None identified | 1)Greater certainty of finances and resources to provide planned services, 25 26 planning completed and there is clarity in terms of the additional financial gap in year that requires closing. 2)There are plans in place to manage demand on acute services and we are looking at all provision in terms of whether it is statutory, VFM etc to seek further efficiencies. Planning will commence shortly for 26 27. | 3 x 3 = 9 | Medium | agreement on uplifts to ensure ending of collective action *relating to new resident drs potential strikes in July 25 | No gaps identified, no action required | August 2025 - budgets shared with understanding of financial gap that requires closing in year, turnaround budget meeting held and non recurrent/recurrent savings identified to support position. Demand management plans are in place and being monitored though there are risks as we are seeing increases in attendances to A&E and others services in primary and secondary care. Further work is being completed with trust and partners to look at what would be need to close beds and release ££s | Place Delegation Arrangements and Effectiveness - Audit of Place governance commenced (as of 30/01/2025) | 07/10/2024 06/01/2025 20/01/2025 30/01/2025 03/03/2025 04/04/2025 06/05/2025 10/06/2025 14/07/2025 18/08/2025 21/08/2025 22/09/2025 | 46013 | Quarterly | Not overdue
1.6.1 - CYP Alliance | Children and Young People (0-25) services are effective and of high quality standards (General Services), The services meet the needs of the children, young people and families living in each Place and the services. Failure to meet this may result in health inequalities | Cathy Winfield Chief Nursing Officer | Nicola Ennis | SY ICB Place Committees | Accountable | South Yorkshire Joint Forward Plan | SY040, SY107, SY127, SY128, IL08 | 1) Ensuring effectiveness of children and young people (CYP) services align with the Joint Forward Plan (JFP), Getting in Right First Time (GIRFT) and the bold ambition best start in life which included waiting lists for community services, elective surgery, mental health services and neurodevelopment assessments. 2) Each Place has specific workplans connected to the recovery of long waits and the key leads from Place are working with provider collaboratives and alliance to support system change in services where appropriate. | 1) Place Boards 2) Provider Collaberatives and Alliance Boards 3) ICB System Leaders Groups | NHSE regional and national reporting | 3 x 3 = 9 | Uncertainty in strategic direction due to pending national guidance. Resource constraints driven by mandated cost reductions to take effect by December 2025. Engagement from key stakeholders. | Unclear prioritisation across stakeholders. | 1) Involve CYP, Families and Carers 2) involve the CYP workforce 3) Involve ICB CYP Place leads and providers 4) involve finance colleagues | 2 x 3 = 6 | Medium | We are working alongside ICB CYP leads to understand Place priorities and the service provision already commissioned. We are reviewing what needs to change to ensure effective services in line with insights shared by CYP e.g. access to services | 1)Await approval of final report following the community mapping exercise, next step to take forward recommendations by end of Q4 25/26. 2)Results of the mapping exercise to be mapped against known quality standards and the financial investment in each service by end of Q4 25/26 | September 2025 - The Acute Federation have completed the community mapping exercise, they have a report and recommendations in draft waiting for final approval and then into the next step to take forward the recommendations. It has been difficult to gain the full financial picture due to a variation in commissioning arrangements however as much as could be understood at this time has been and this aspect of the work has been completed. | No | 22/10/2024 07/01/2025 31/03/2025 18/08/2025 30/09/2025 | 46111 | Six-Monthly | Not overdue
1.6.2.1. | The ICB is meeting its statutory safeguarding responsibilities | Cathy Winfield Chief Nursing Officer | Andrew Russell | Place Committee | Accountable | South Yorkshire Joint Forward Plan | SY040, SY107, SY127, SY128 | SY Children and Young People Alliance | 1) Safeguarding - Place Based Local Safeguarding Partnerships. 2) ICB System - Safeguarding Oversight and Assurance Meeting (SOAM), QPIE. | 1) Local Safeguarding Partnerships 2) NHS E Regional and National Teams 3) CQC | 3 x 3 = 9 | A South Yorkshire four Place differing approach to safeguarding Implementation of the co-design and Insights work undertaken over the previous 12 months. Single system safegaurding dashboard | A single system approach to data monitoring, risk oversight and escalation. | 1) Involve CYP 2) Health Equity Collaborative 3) Long term conditions 4) New service models & pilots eg core connect 5) Children and young people mental health | 3 x 2 = 6 | Medium | Safeguarding teams are well established and safeguarding approach at ICB is well established. Mechanisms of assurance is in place at Place, further work being undertaken to bring it together as an ICB system | 1) Populate and submit the NHS Digital Safeguarding dashboard requirements aligned to NHS E Quarterly Audits, and bi-monthly to Safeguarding Oversight and Assurance Meeting (SOAM) throughout 25/26, with aim to achieve by Q4 25/26 2) Further develop the oversight and assurance framework for safeguarding across all 4 areas and report into QIPPE at a system level by end of Q3 25/26 | 0 | No | 30/10/2024 07/01/2025 27/03/2025 21/07/2025 | 46043 | Six-Monthly | Not overdue
1.6.2.2 | Children and Young People (0-25) services are effective (SEND) | Cathy Winfield Chief Nursing Officer | Andrea Ibbeson | Place Committees and SY ICB SEND Board | Accountable | South Yorkshire Joint Forward Plan | SY040, SY107, SY127, SY128 | SY Children and Young People Alliance | 1) SEND - SEND place based multi-agency boards 2) ICB System - ICB SEND Board (chaired by Chief Nurse Officer), QPIE | 1) Place Based MA SEND Board 2) NHS E Regional and National Teams 3) CQC | 3 x 3 = 9 | Staffing - identified that there is a need for a Head of SEND to support the ICB to carry out statutory obligations of the SEND agenda Rotherham - Designated Clinical Officer (DCO) WTE as currently at 0.8 | Dashboard that will offer full understanding of performance and quality matrix for the system. | 1) Involve CYP 2) Health Equity Collaborative 3) Long term conditions 4) New service models & pilots eg core connect 5) Children and young people mental health | 3 x 2 = 6 | Medium | Designated clinical officers and transformation leads at Place are well established alongside the required partnership working at Place. Further work to be undertaken to bring together as an ICB system | 1) Plan to recruit a Head of SEND is currently on hold whilst organisational change is being worked through during 2025/6. This may extend to beyond this financial year, pending further announcements. 2)Roles and responsibilities are being reviewed as part of a wider piece of work to support the organisational change process during 2025/6. This may extend to beyond this financial year, pending further announcements. 3) Continue to develop a SEND dashboard throughout 2025/26, which may face delay in light of the current organisational change process. | 24/03/25 - ICB SEND Board is established, first meeting held in October in 2024. Clear reporting structures have been formed and are now established. This provides assurances to QPPIE and ICB Executive Leads. We continue to meet with service users and families at each place to ensure their voices are heard and acted upon. | No | 30/10/2024 11/11/2024 07/01/2025 27/03/2025 17/07/2025 30/09/2025 | 46111 | Six-Monthly | Not overdue
1.6.3. | Children and Young People (0-25) services are effective (Mental Health, LD and Autism) Specifically for mental health this includes: • Implementation of Mental Health Support Teams in Schools • A comprehensive offer for 0-25 year olds that reaches across mental health services for CYP and adults. • The 95% CYP Eating Disorder referral to treatment time standards and the proportion of CYP waiting 4 weeks or less to start receiving help achieved • 100% coverage of 24/7 mental health crisis care provision for children and young people which combines crisis assessment, brief response and intensive home treatment functions • Delivery of the CYP inpatient transformation plan (led by specialised collaborative) • CYP mental health plans will align with those for children and young people with learning disability, autism, special educational needs and disability (SEND), children and young people’s services, and health and justice | Chris Edwards Rotherham Place Director | Kelly Glover | Place Committee | Accountable | South Yorkshire Joint Forward Plan | SY040, SY107, SY127, SY128 | 1) Development and implementation of effective system-wide and Place Operational Plans to deliver LTP B35 planning objectives 2) Effective delivery management processes at place including internal ICB escalation and system level oversight 3) Effective patient experience and engagement process to support delivery undertaken by VCSE partner 4) Focus on delivering the ambitions of the Integrated Care Strategy and 5 year ICB Plan with a focus on early intervention and prevention | 1) ICB Place Committees 2) MHLDDA SDG 3) Senior Leadership Executive 4) Operational Executive 5) Board | NHSE Assurance process | 3 x 3 = 9 | Sufficient Funding and Workforce | ICB Level assurance of neurodiversity pathways that we are effectively tackling issues around neurodiversity in each Place and at system | 1) Involve CYP 2) Health Equity Collaborative 3) Long term conditions 4) New service models & pilots eg core connect 5) Children and young people mental health 6)Family hubs 7)Full usage of targeted SDF | 3 x 2 = 6 | Medium | The collaboratives, ICB programmes and places are working to clarify who is leading what to ensure clarity around what the priorities are across the system and who is leading and contributing to which elements. Data to support a number of the metrics is flowing again giving assurances that access to services is improving, 2 new NHSTs will be coming onboard and all places have 24/7 crisis provision. | 1) ICB level and Place level oversight of deliverables and adherence to access and waiting times standards, ongoing quarterly throughout 25/26. 2) Places to focus on local pathways and developments – including phase 2 of the Partnership for inclusion in schools (PINS) project, by Q4 25/26 with the evaluation continuing through 26/27 3) LDA Programme to focus on SY-Wide approaches – including expansion of the All Age LDA Key-working service which will conclude phase 2 by Q4 25/26 with the Adult Proof of concept running through to 26/27 following the completion of the evaluation in 27/28, PINS project oversight and set up of SY community of practice and the sharing and learning of the CYP Projects to conclude by Q4 25/26 with evaluation for PINS continuing into 26/27 4) MH and LDA portfolio directors to continue collaborative work towards the CYP Inpatient transformation programme, led by the Specialised Provider Collaborative 5) Delivery and implementation of agreed recommendations following the review around ASD/ADHD priorities. This will be ICB-led (Sheffield Place Deputy Director team) who will oversee the recommendations working closely with Provider Collaborative and other partners with some elements of the work to be completed by Q4 25/26 with implementation commencing 26/27 and remaining recommendations to be worked through in 26/27. 6) Implement individual place programme plans by Q4 25/26 | September 2025 - The Review of CYP LDA programme to ensure alignment with provider collaborative led programmes has now concluded, with the outcome that Places will focus on local pathways and developments including phase 2 of the PINS project. Significant work has been undertaken by the Provider Collaborative relating to the delivery of all-age ASD/ADHD workstream following review. it was agreed that there needed to be a more achievable and timely approach to addressing the challenges. A proposed approach and recommendations has been agreed via a paper submitted to SLE in September. This will be led by the ICB (Ian Atkinson’s team from Sheffield Place) who will oversee the recommendations agreed working closely with the Provider Collaborative and other partners. The MHST teams from 2024/25 are now live in Doncaster and Barnsley. In addition, in 2025/26 financial year a further 4 MHSTs have been awarded as follows: 1x Doncaster, 1x Rotherham and 2x Sheffield – it is anticipated that these will help to further access to CYP mental health services over the coming years. On CYP mental health access targets during the 2025/26 planning round there was agreement on what items should be reported via the MHSDS and this is now in place across all places/providers. Best practice is shared via the SY ICB CYP Mental Health Steering Group and risks/mitigations are raised at the steering group as required. | No | 03/10/2024 06/01/2025 20/01/2025 27/01/2025 03/03/2025 10/03/2025 27/03/2025 06/05/2025 10/06/2025 14/07/2025 22/09/2025 | 46103 | Six-Monthly | Not overdue
1.7. | The ICB has a programme of work in place to strengthen and accelerate our focus on prevention and early identification that has a focus on where it can have the most impact in improving outcomes; i) on the four main modifiable risk factors of smoking, healthy weight (diet and physical activity), alcohol and hypertension, ii) improved management of long term conditions which are the main causes of premature mortality in South Yorkshire (cardiovascular and respiratory) in order to delay and prevent co-morbidity from occurring. | Dr David Crichton Chief Medical Officer | Lisa Wilkins David Lautman | Pop Health and Health Inequalities SDG, Place Committee | Accountable | South Yorkshire Joint Forward Plan | SY044 | 1) To give clear oversight Prevention and LTC papers detailing progress against JFP priorities will be tabled at Pop Health and HI SDG and Board. 2) South Yorkshire wide work on prevention and LTC is led by the Prevention and Public Health Team (Medical Directorate) together with the Population Health Team (also in the Medical Directorate). The Prevention/Pop Health teams coordinate input to strategy development (linking with Place Transformation and Delivery Managers), directly lead on some programme delivery on behalf of the ICB across SY and support or coordinate other programmes which are primarily delivered via Places. 3) The majority of the delivery of prevention/LTC transformation and delivery occurs at Place by the transformation teams and through Place partnerships. 4) The South Yorkshire wide and Place priorities are informed by the Joint Forward Plan, NHS planning Guidance, Integrated Care Partnership's strategy and Place partnership strategies. In 25/26 we are expecting the publication of a 10 year Health Plan which will further guide this work. 5) Physical Health and Prevention Programmes are further supported by the Clinical Programmes team at NHSE NEY Regional Team. | 1) x4 Place Partnership Committees 2) SY SDG Population Health and HI's 3) SY SDG Prevention & LTC Subgroup | NEY NHSE Regional meetings (NEY Prevention Board and NEY Physical Health Board) | 3 x 3 = 9 | 1) Limited ICB budget for prevention, with system wide prevention initiatives predominately funded non recurrently leading to non sustainable services and difficulty with recruitment and retention of staff 2) SDF funding no longer ring fenced plus overall financial position limiting funding for prevention and LTC transformation 3) Limited ICB capacity to accelerate progress combined with (in some cases) non alignment of priorities across the Places +/- SY wide working resulting in slower progress than would otherwise be possible 4) System level prevention posts funded from non recurrent 'SDF' funding that is no longer ring fenced. Two fixed term extended to March 26. 3 people on secondment/GP contractor currently til end Dec but asking Exec next week to consider extended to end March 26 5) Lack of a SY clinical pathway for people with obesity resulting in unmet need and inability to comply with the existing and new NICE TAs for weight management related drugs. Huge risk to primary care capacity and to funding of costs of implementation of NICE TAs for weight management drugs, including Tirzepatide 6) Lack of an alcohol care team at DBTH. Risk to funding to the STH Alcohol team - awaiting confirmation that Trust funding. 7) Cardiac and pulmonary rehabilitation uptake/provision not meeting national targets and reduction in SDF funding limiting potential to address this 8) Unwarranted variation in care in primary care for primary and secondary prevention and lack of a SY wide approach and capacity to support practices to reduce the variation | 1) Lack of clarity of accountability due to the combination of Place and SY wide working 2) Organisational change resulting in likely loss of staff/capacity, loss organisational memory and possible change in governance structures | 1)Shift in mindset and resources to invest and support prevention and LTC management with recurrent funding and sufficient capacity to enable a step change on a sustainable basis at sufficient scale to have a population health impact. 2)Implementation of a SY approach to supporting practices that have the greatest unwarranted variation, which not only looks at clinical/holistic management but also the underlying structure and organisation of the practices. 3)Awaiting national delivery plan / operating planning guidance. But ongoing work does all align with 10 year plan. | 3 x 3 = 9 | Medium | UCL Institute of Health Equity, England’s Widening Health Gap: Local Places Falling Behind and life expectancy falling. | 1) Codesign of a SY wide obesity clinical care pathway and implementation of the Tirzepatide and other NICE TAs for weight management drugs and development of supporting business case. Optional appraisal/business case to be presented to Executive by June 26. 2) Doncaster Place transformation colleagues to continue to work with RDASH and DBTH to remodel inpatient alcohol care services to an ACT model throughout 2025/6 3) Continue to liaise with STH regarding Trust internal funding for ACT and raise via contracting routethroughout 2025/6 4) Continue to work with Cardiac and Pulmonary rehabilitation teams to enhance pathways, raise awareness of CR/PR eligibility criteria in primary care, invest 'SDF' funding to increase skill mix of teams to avoid scarce specialist clinical team being spent on non clinical duties and increase the use of digital rehab. By end of March 26 5) Alignment of place / system priorities via the I&V process - Q1 and Q2 25/26 6) Confirm extension of contracts for fixed term prevention / LTC posts, which may be delayed due to the recent announcement re: running cost reductions expected to be finalised by Q3 25/6 7) Ensure key focus of SY 10 year plan is on enhancing prevention and LTC management and includes the development of a SY approach that is sufficiently resources to support practices who have the greatest unwarranted variation. This may also require a review on whether practices in the most deprived areas require additional funding, throughout 2025/6 8) Confirm prevention/LTC SDF budget and move to recurrent rather than non recurrent funding, which may be delayed due to the recent announcement re: ICB cost reductions expected to be finalised by Q3 25/6 | June 2025 - Financial challenges: SDF funding is no longer ringfenced for programmes of work which will potentially limited progress. Limited SY wide and Place Transformation Capacity. Obesity transformation task group established in April 2025, project planning and HNA commenced; Information given to STH to support their internal ACT B'ness case; Awaiting confirmation of SDF funding; clinical lead and other prevention fixed term contracts extended to June 25; Consultant in PHM attending I&V meetings to enhance connectivity with Place Deputy Directors; prevention/LTC 'stock check' underway. Organisation change process being undertaken in line with the Strategic Commissioning direction within the ICB blueprint document. | Repeat 360 internal Audit | 23/08/2024 22/11/2024 24/02/2025 10/04/2025 18/08/2025 | 45979 | Quarterly | Not overdue
1.8 - R | Primary care services are effective in Place. | Chris Edwards Rotherham Place Director | Claire Smith | System Leadership Executive Group supported by: Place Committee | Accountable | South Yorkshire Joint Forward Plan | SY079, SY069, SY061, SY132, IL03 | 1)Place Primary Care meetings; 2)Primary Care Delivery Group chaired by Deputy Place Director, decisions record and may go through Place Executive Team (meets weekly) where appropriate. 3)Oversight by Rotherham PLACE board 4) LMC officers meeting monthly supporting relationships and agreeing approaches collectively 5) Rotherham is now a pilot site for Neighbourhood working and have developed further membership of the Place board to include CD rep and there is an identified Place team to support the national pilot including several representatives from PC who have been voted in by PC colleagues democratically | Operational Executive | Annual update to Health Select committee | 3 x 3 = 9 | none identified | none identified | agreement on uplifts to ensure ending of collective action *relating to new resident drs potential strikes in future | 2 x 3 = 6 | High | Place Primary Care meetings; Primary Care Delivery Group chaired by Deputy Place Director, decisions record and may go through Place Executive Team (meets weekly) where appropriate. Oversight by Rotherham PLACE board. LMC officers meeting and attendance at CDs. Primary Care Place team fully recruited to supporting primary care. Place Primary Care meetings; Primary Care Delivery Group chaired by Deputy Place Director, decisions record and may go through Place Executive Team (meets weekly) where appropriate. Oversight by Rotherham PLACE board. LMC officers meeting and attendance at CDs. Primary Care Place team fully recruited to supporting primary care. See above re addition in terms of engagement with PC on Neighbourhood national pilot. | No gaps identified, no action required | 0 | Audit improvements in population health outcomes in 25/26 | 07/10/2024 11/11/2024 16/12/2024 06/01/2025 30/01/2025 03/03/2025 04/04/2025 06/05/2025 10/06/2025 14/07/2025 18/08/2025 21/08/2025 22/09/2025 01/10/2025 | 46113 | Six-Monthly | Not overdue
Objective 2: Tackle Inequalities in Outcomes, Experience and Access - Executive Lead - Chief Medical Officer | [10 empty] | Risk Appetite 9 |  |  | Risk Appetite 9
2.1.. | Through effective Place Partnership Plans, the ICB is tackling inequalities and moving towards greater self-care prevention and patient empowerment. | Dr David Crichton Chief Medical Officer | Lisa Kell | Place Committees | Accountable | South Yorkshire Joint Forward Plan / BAF 2023 | SY021, SY042, SY061, SY044 | 1) PHM SDG - In full please 2) Digital Research Innovation (DRI) SDG 3) ICS Constitution sets out statutory duties 4) ICS Engagement and Involvement Strategy and policies 5) Place Communication & Engagement Plan 6) Strong relationship with Healthwatch 7) Health & Wellbeing Board - local collaborative work to improve health outcomes and address health inequalities. 8) Place Strategy and Place Delivery Plans 9) Integrated Care Partnership Strategy 10) Population Health Needs Assessment 11) Joint Forward Plan - ICP strategy and comprehensive public engagement on population needs. 12) SY Digital strategy to develop PHM infrastructure, i.e. shared data platform PHM digital tech and implementation across SY (both for direct patient care and service planning purposes). | 1) SY Population health SDG and 360 HI audit action plan Digital Research and innovation SDG. 2) Outcomes framework and Dashboard 3) Integrated Care Strategy 4) x 4 Place Partnership Committees | 1) 360 Internal Audit on HIs completed with considerations , action plan developed and owned by Pop h SDG was presented at QPPIE 8/8, Action plan progress to be presented to QPIE going forward 2) NHSE Assurance Framework 3) CQC | 4 x 3 = 12 | Recent announcements regarding NHSE and ICBs highlights uncertainty of the roles and functions going forward. Sufficient resources required to undertake the work required to facilitate work that reduces health inequalities and inequity of access ( investment £ and capacity / resources) | Recent announcements regarding NHSE and ICBs highlights uncertainty of the roles and functions going forward. Sufficient resources required to undertake the work required to facilitate work that reduces health inequalities and inequity of access ( investment £ and capacity / resources) | 1) Health Care related Inequalities are clearly reported in equivalence with other ICB Duties Through pop health outcomes framework and dashboard (within the Integrated Performance Report (IPR) 2) Implementation of the 360 internal audit HIs action plan and annual HI internal audit, has taken longer than originally intended | 4 x 2 = 8 | Medium | This is one of the main ICB core aims and is embedded into all strategy and delivery plans across the ICS. Regularly discussed through the delivery group, place partnership meetings and the ICB Board | 1)Clear line-of-sight for Health Inequalities investment in the 2025/26 2)Operating and Financial Plan - Final sign-off in April 2025 ICB Board 3)Refresh of ICB 5-year Joint Forward plan and we await the publication of the NHS 10 year plan expected May 2025 4)Input into the Change.NHS engagement in the 10 year health plan, implement the Plan from May 2025 5) Effective Reporting of progress being made and mainstreaming in the updated Integrated Performance Report which will continued to be reviewed 6-monthly throughout 2025/6 6) 360 Internal Audit HI completed previously, progress report to be presented to QPIE by August 2025 | September 2025 - Opportunity for the ICB to express an interest in becoming a prevention accelerator. | RE-audit of the 360 work previously undertaken | 07/08/2024 11/11/2024 10/02/2025 31/03/2025 30/06/2025 29/09/2025 | 45745 | Quarterly | Not overdue
2.7.1 - R | The ICB works collaboratively with partners to improve health, care and reduce inequalities | Chris Edwards Rotherham Place Director | Claire Smith | Place Committee | Accountable | South Yorkshire Joint Forward Plan | SY028, SY115, SY116, SY117, SY124, SY079, SY113, SY021, SY040, SY082, SY044, SY066 | 1) Rotherham Health and Care Place Plan details plans and is overseen by the Rotherham place board and the Health and Wellbeing board. 2) Plan is also signed off by all statutory partners, VAR and Connect Healthcare. | 1) Rotherham Place ICB board sub committee. alongside the Place Plan there is a Population Health and Inequalities strategy developed through a steering group chaired by the public health Director and Deputy Place Director ICB - an action plan is monitored through this group and the Place Board / H&WB. | Rotherham Health and Welbeing Board | 3 x 4 = 12 | None identified | None identified | 1)Delivery of Place Plan priorities and our Health Inequalities Strategy - action plan. Agreement on what Place Board looks like once changes have been implemented to meet the new ICB model 2)Delivery of key priorities with the H&WB strategy 3)Continually holding partners to account for decisions made that impact our population 4)Working in continued collaboration taking appropriate business through Place | 2 x 3 = 6 | Medium | Partnership approach and collaboration is well established and embedded in our Place governance however, the financial positions of organisations pose a risk to ensuring we work in collaboration to ensure health inequalities are addressed | No gaps identified, no action required | January 2025 - recommendation for this risk to be SY Wide April 2025 - Revision of health and care place plan, currently ongoing, to be completed by May 2025 | Audit outcomes, experience and access | 07/10/2024 11/11/2024 16/12/2024 06/01/2025 30/01/2025 03/03/2025 04/04/2025 06/05/2025 10/06/2025 14/07/2025 18/08/2025 21/08/2025 22/09/2025 | 46103 | Six-Monthly | Not overdue
2.12 - B | Integrated services supporting people in the community are working well failure to meet this may result in more people requiring hospital care as a result of their needs not being met in the Community | Katie Calvin-Thomas Barnsley Place Director | Jamie Wike | ICB Place Committees | Accountable | South Yorkshire Joint Forward Plan | SY069, SY107, IL17 | 1)Place Partnership Delivery Group 2)Performance and Quality Reports 3) Contract Management Arrangements 4) Place Plan - 5 Goals and clear deliverables 5) Transformation Priorities for Place Partnership 6) Transformation and Delivery Work Programme | Place Partnership Board and Place Committee | CQC Inspection and oversight of regulated services | 3 x 3 = 9 | Intermediate care - Long term sustainable model for bed and community based IC service | No gaps identified | 1)Integrated neighbourhood team - further development and expansion into broader Neighbourhood Health offer 2)Palliative and end of life care 3)Business case for IC approved | 2 x 3 = 6 | High | Integrated Community Neighbourhood Teams model in place for community healthcare and strong partnership arrangements with adult social care and primary care. | No gaps identified, therefore no action required at this time | Sept 2025 - Proposals to move to new IC model being finalised with some amends to bed base model as it has not been feasible to create a single site 50 bed unit. Partnership discussions are ongoing around the Barnsley approach to Neighbourhood Health and taking forward to proposals that were included in the Barnsley application to be part of the NNHIP which whilst unsuccessful, partners still want to progress. Positive results being seen around work across health and social care including out of hours response, frailty clinics in Neighbourhoods, support in Care Homes etc. | No | 25/09/2024 11/11/2025 10/02/2025 27/03/2025 30/05/2025 04/07/2025 14/08/2025 18/09/2025 | 46099 | Six-monthly | Not overdue
Objective 3: Enhance Productivity and Value for Money - Executive Lead - Chief Finance Officer | [10 empty] | Risk Appetite 9 |  |  | Risk Appetite 9
3.9. | The ICB effectively uses of digital and data to better understand and enable transformation of productivity and VfM in health and care delivery | Dr David Crichton Chief Medical Officer | Kieran Baker | ICB Board IG Group (Covering Cyber, Digital and Data Security, Clinical Safety) Place Committees Quality Performance Patient Involvement Experience (QPPIE) | Accountable | South Yorkshire Joint Forward Plan | SY044; SY061 | 1) ICS Data and Insight Strategy 2) ICS Digital Strategy 3) Digital, Research and Innovation SDG 4) ICS Cyber Strategy | 1) Digital, Data and Technology Delivery Oversight Group 2) South Yorkshire Cyber Forum | 1) 360 Audit - Data Strategy 2) 360 Audit - Data Quality and Performance Management 3) NHSE NEY Digital Transformation Programme | 2 x 2 = 4 | SY ICS Digital, Data and Technology Workforce Plan Implementation of Eclipse Vista aross all South Yorkshire Places | No gaps identified | 1) Development of analytical approach to population health management (Initiative 5 of the ICS Data and Insight Strategy) 2) Improvement in scope and standardisation of Shared Care Records in South Yorkshire. 3) Roll-out Eclipse Risk Stratification across South Yorkshire 4) Ingestion of Primary Care (GP) data into the South Yorkshire Data Platform to support data linkage and better understanding of patient health and care requirements to support improved decision-making. | 2 x 1 = 2 | Medium | Work continuing through the Improvement and Value Group, led by Lee Outhwaite to ensure that we are utilising our data effectively to enable insight-driven decision-making. New analytical products are being built alongside place colleagues so that opportunities for improvement can be identified. Also, work is taking place PMO to improve reporting of benefits alongside transformation activities. | 1) To finalise and begin implementation of the DDAT workforce strategy by Q1 25/26 (this is inclusive of viable SCR product, 'Connected South Yorkshire rollout, inclusion of qualitative public insight into the SY Data platform. pathways costing model) 2) To implement Eclipse across all GPs in South Yorkshire - currently at 93% adoption across GP practices to be completed by end of Q2 25/26 | June 2025 - Currently rolling out Co-Pilot licenses to improve productivity as well as working with system partners to implement an AI adoption framework for the safe adoption of AI in clinical and administrative processes. | No | 21/10/2024 13/03/2025 27/03/2025 30/06/2025 | 46203 | Annually | Not overdue
3.10. | The ICB is improving digital inclusion to ensure optimal use of digital and data solutions for our citizens and wider population | Dr David Crichton Chief Medical Officer | Kieran Baker | ICB Board IG Group (Covering Cyber, Digital and Data Security, Clinical Safety) Place Committees Quality Performance Patient Involvement Experience (QPPIE) | Accountable | South Yorkshire Joint Forward Plan | SY044; SY061 | 1) ICS Data and Insight Strategy 2) ICS Digital Strategy 3) ICS Cyber Strategy 4) Digital, Research and Innovation SDG | Digital, Data and Technology Delivery Oversight Group | 1) NHSE NEY Digital Transformation Programme 2) Primary Care Alliance 3) SY Digital Inclusion Audit | 2 x 2 = 4 | ICS Digital Strategy refresh - new strategy approved by ICB Executive and will be shared with System Leaders Executive. Digital Services for Our Public Programme (DSOP) - this work is underway and has been folded into the Growth Accelerator programme. | No gaps in assurance | Creating a standardised approach across all four places for supporting our South Yorkshire population navigate an increasingly digital society between 2024 and 2026 | 2 x 1 = 2 | High | Dedicated programmes of work supporting development of this agenda are being reviewed and shared with Board. Working closely with VCSE alliance on a new digital offer for our public. Improvements to adoption of tools such as GP Online Registration and NHSApp. | 1) ICS digital strategy is being finalised following system wide discovery sessions. Implementation to begin during Q1 25/26 2) DSOP - Work currently underway with VCSE Alliance and pathways to work programme to review options and opportunities to implement system wide digital 'front door' to enable our public to access commissioners and non-commissioned services by the end of Q2 25/26 | 18/08/2025: The new ICS Digital Strategy has been approved by ICB Executive and will be shared with System Leaders Executive before publication on the ICS website and transition into the delivery phase with system partners. | No | 20/01/2025 13/03/2025 19/03/2025 30/06/2025 18/08/2025 | 46252 | Annually | Not overdue
Objective 4: Help the NHS Support Broader Social and Economic Value - Executive Lead, Director of Strategy & Partnerships | [10 empty] | Risk Appetite 9 |  |  | Risk Appetite 9
4.9 - R | Our work with people and communities is effective | Chris Edwards Rotherham Place Director | Claire Smith | Place Committees | Accountable | South Yorkshire Joint Forward Plan | No link | 1) ICB Involvement Team & wider network 2) Places, Provider Collaboratives and Alliances 3) Rotherham Chief Execs meeting | Rotherham Place ICB board sub committee | Health and Wellbeing Board. | 3 x 4 = 12 | A robust plan for all transformation/commissioning activity is needed which incorporates engagement with communities | EQIA completion for all activity that requires one | 1)Put the voices of people and communities into decision making 2)Embed mechanisms to enable citizen involvement to play a key role in the system focus on tackling health inequalities 3)Work with people and communities on the priorities identified in JFP | 2 x 3 = 6 | Medium | Rotherham place plan and Rotherham together partnership plan focusses on social value and the role of anchor organisations. ICB place team part of Rowntree review on anchors and signed up to social value charter and staff trained RTP leading on social value and training for key staff in contracting and procurement as well as senior officers | EQIAs to be completed for all commissioning activity and taken to Place Executive for assurance and sign off, this is to be completed as required. Ongoing as required through 2025/6 | January 2025 - recommendation for this risk to be SY Wide | Audit ICB contribution to social value | 07/10/2024 11/11/2024 16/12/2024 06/01/2025 20/01/2025 30/01/2025 03/03/2025 04/04/2025 06/05/2025 10/06/2025 14/07/2025 18/08/2025 21/08/2025 22/09/2025 | 46103 | Six-Monthly | Not overdue
4.11 - R | Our work with local authority is effective | Chris Edwards Rotherham Place Director | Claire Smith | ICB Place Committees | Accountable | South Yorkshire Joint Forward Plan | SY107, SY124, SY021 | 1) Rotherham PLACE partnership is co- chaired by ICB RMBC. 2) Plans are signed off by both organisations. HWBB strategy signed off by both organisations. 3) Senior joint posts across key work areas. Health attend Rotherham Partnership Board chaired by RMBC Chief Exec and attend Health Scrutiny routinely. 4) ICB key member of Rotherham Together Partnership which is leading the way on maximising social vlaue | Rotherham Place ICB board sub committee | Health and Well Being Board | 2 x 3 = 6 | No gap identifed | No gap identifed | Support and strengthen our partnership arrangements in our places and our SY Integrated Care Partnership | 2 x 2 = 4 | High | Rotherham partnership works closely on social value. All partners signed up to the social value charter and key staff have had social value training. there are social value champions identified in our team and RMBC are leading on task and finish group to implement best practice | No gaps identified, no action required | April 2025 - Continue frequent meetings as a joint senior management group with Council colleagues regarding commissioning decisions Review how they work and review attendance - aim to support transparency over workstreams and key priorities/risks within our organisations to manage and mitigate impact across H&SC on decisions. Meetings working well and continue to use as a platform to discuss partnership working particularly in difficult decision across organisations to prevent unintended impact. Review to be completed by end of Q2 25/26 | Audit BCF arrangements - internal audit completed as part of preparation for 25/26. understanding of budget lines and services within s75, agreement of prioirty of spend in IBCF | 07/10/2024 11/11/2024 16/12/2024 06/01/2025 20/01/2025 30/01/2025 03/03/2025 04/04/2025 06/05/2025 10/06/2025 14/07/2025 18/08/2025 21/08/2025 22/09/2025 | 46103 | Six-Monthly | Not overdue

## 8. Organogram
Updated 05.08.2024
OVERSIGHT |  |  |  |  | ASSURANCE
Audit and Risk | Finance and Investment | OE (?FE) | People Workforce and Culture | QIPPE | Barnsley Place Committee | Doncaster Place Committee | Rotherham Place Committee | Sheffield Place Committee | South Yorkshire IG Group | SY ICB Health and Safety Group | Medicines Optimisation Assurance Group | Local Health Resillience Partnership (LHRP) | SY UEC Alliance Board | Palliative End of Life Care Strategic and Transformation Board | Infection Control Group | Primary Care Committee | System Quality Group | Rotherham PET | QIPPE | Operational Executive (?FE)
[9 empty] | Below Risk Appetite | Below Risk Appetite |  | Below Risk Appetite |  | Below Risk Appetite |  |  |  | Below Risk Appetite
Below Risk Appetite
Below Risk Appetite
[5 empty] | Below Risk Appetite | Below Risk Appetite | Below Risk Appetite | Below Risk Appetite
Below Risk Appetite
SY028: Cancer - Oncology Workforce Challenges
Accountable
16
SY115: Cancer - Operational Recovery
Accountable
16
SY116: Cancer - Operational Recovery
Accountable
16
SY117: Cancer - Paediatric Radiotherapy
Accountable
16
SY016: Fraud - CHC/PBH
Responsible
9
SY061: Access to Primary Care
Accountable
9
SY112: Fraud - Pharmacy Dispensing
Accountable
9
SY019: Information Governance -Information Sharing
Responsible
6
SY049: Compliance with Policies at Place
Responsible
6
SY062: Information Governance - Personal Devices
Responsible
6
SY078: Information Governance Lack of Function
Responsible
6
SY011: EPRR Arrangements
Responsible
4
SY017: Fire Regulations
Responsible
3
SY133: Information Governance - Primary Care Data
Responsible
1
SY042: Finance Service Delivery
Accountable
20
SY132: GP Action
Accountable
16
SY091: Corporate ICB Capacity
Accountable
12
SY131: Infection Control
Responsible
15
SY128: Paediatric Hearing Services
Accountable
12
SY124: National Trajectory for Learning Disability and Autism Inpatients
Responsible
12
SY021: LeDeR
Responsible
12
SY0113: Waiting Times
Accountable
12
SY0123: Complaints Capacity
Responsible
12
SY040: CAMHS
Accountable
12
SY108: Infection Prevention Control
Accountable
12
SY082: Adult Mental Health
Accountable
9
SY044: Tackling Health Inequalities
Accountable
9
SY066: Delayed Discharge from Hospital both Acute and MH
Accountable
9
SY069: Primary Care Delegation
Accountable
9
SY079: Primary Care Partnership working
Accountable
6
SY0106: Trauma Resilience Service
Accountable
4
SY0107: Community Paediatrics/Childrens Pathways
Responsible
12
SY042: Finance Service Delivery
Accountable
16
SY042: Finance Service Delivery
Accountable
16
SY042: Finance Service Delivery
Accountable
16
SY042: Finance Service Delivery
Accountable
16
SY124: National Trajectory for Learning Disability and Autism Inpatients
Responsible
12
SY124: National Trajectory for Learning Disability and Autism Inpatients
Responsible
12
SY124: National Trajectory for Learning Disability and Autism Inpatients
Responsible
12
SY124: National Trajectory for Learning Disability and Autism Inpatients
Responsible
12
SY021: LeDeR
Responsible
12
SY021: LeDeR
Responsible
12
SY021: LeDeR
Responsible
12
SY021: LeDeR
Responsible
12
SY0113: Waiting Times
Accountable
12
SY0113: Waiting Times
Accountable
12
SY0113: Waiting Times
Accountable
12
SY0113: Waiting Times
Accountable
12
SY040: CAMHS
Accountable
12
SY040: CAMHS
Accountable
12
SY040: CAMHS
Accountable
12
SY040: CAMHS
Accountable
12
SY0107: Community Paediatrics/Childrens Pathways
Responsible
12
SY0107: Community Paediatrics/Childrens Pathways
Responsible
12
SY0107: Community Paediatrics/Childrens Pathways
Responsible
12
SY0107: Community Paediatrics/Childrens Pathways
Responsible
12
SY082: Adult Mental Health
Accountable
9
SY082: Adult Mental Health
Accountable
9
SY082: Adult Mental Health
Accountable
9
SY082: Adult Mental Health
Accountable
9
SY016: Fraud - CHC/PBH
Responsible
9
SY016: Fraud - CHC/PBH
Responsible
9
SY016: Fraud - CHC/PBH
Responsible
9
SY016: Fraud - CHC/PBH
Responsible
9
SY044: Tackling Health Inequalities
Accountable
9
SY044: Tackling Health Inequalities
Accountable
9
SY044: Tackling Health Inequalities
Accountable
9
SY044: Tackling Health Inequalities
Accountable
9
SY061: Access to Primary Care
Accountable
9
SY061: Access to Primary Care
Accountable
9
SY061: Access to Primary Care
Accountable
9
SY061: Access to Primary Care
Accountable
9
SY066: Delayed Discharge from Hospital both Acute and MH
Accountable
9
SY066: Delayed Discharge from Hospital both Acute and MH
Accountable
9
SY066: Delayed Discharge from Hospital both Acute and MH
Accountable
9
SY066: Delayed Discharge from Hospital both Acute and MH
Accountable
9
SY017: Fire Regulations
Responsible
3
SY133: Information Governance - Primary Care Data
Responsible
1
SY049: Compliance with Policies at Place
Responsible
6
SY049: Compliance with Policies at Place
Responsible
6
SY049: Compliance with Policies at Place
Responsible
6
SY049: Compliance with Policies at Place
Responsible
6
SY131: Infection Control
Responsible
15
SY011: EPRR Arrangements
Responsible
4
SY112: Fraud - Pharmacy Dispensing
Accountable
9
SY127: Children and Young People
Consulted
4
SY132: GP Action
Accountable
16
SY069: Primary Care Delegation
Accountable
9
SY079: Primary Care Partnership working
Accountable
6
SY028: Cancer - Oncology Workforce Challenges
Accountable
16
SY0106: Trauma Resilience Service
Accountable
4
SY063: UTC Centre National Requirements, Sheffield Accountable
12
SY128: Paediatric Hearing Services
Accountable
12
SY091: Corporate ICB Capacity
Accountable
12

## 10(iii) Rotherham RR
[6 empty] | Initial Risk Score | [6 empty] | Residual Risk Score
Ref | Place | Category | Domain | Link to Board Assurance Framework | Risk Description | Likelihood | Impact | Score | RACI | Mitigation / Treatment | Lead risk owner | Source of Risk | Likelihood. | Impact | Residual Score | Date risk assessed | Next assessment due | Days Overdue | Person Responsible for Updates | Progress / Update | Date for reassessment | Assurance | Oversight | Date added to RR | Month added to RR | Number of days open | Commentary to Support Review
SY124 | ICB | Mental Health Services inc. LD/Autism/CAMHS | 1,3,5,6 | BAF 1.1.1D, BAF 1.1.1B, BAF 1.1.1R, BAF 1.1.1S, BAF 1.4.1, BAF 1.4.2, BAF 1.4.3.1V, BAF 1.4.3.1CYP, BAF 1.4.3.1B. BAF, 1.4.3.1D, BAF 1.4.3.1R, BAF 1.4.3.1S, BAF 2.10, BAF 3.11, BAF 4.4 | National Trajectory for Learning Disability and Autism (LDA) Inpatients - There is a risk that the ICB will not meet the national trajectory for 24/25 based on no more than 30 inpatients per 1 million population, this is due to an increased number of admissions across all 4 places and a number of inpatients who are stuck in hospital with no clear discharge plans, this is also resulting in increased out of area placements being required which is having a significant impact on budgets due to the high cost packages involved with the spot purchased placements | 4 | 4 | 16 | Accountable | 1)Regular Case Reviews with place and Programme Director to identify and unblock barriers to discharge 2)Expansion of Children and Young People Keyworker Programme – Prevent risk of admission, facilitate discharge promptly 3)Development of Safe Place/Crisis beds as part of the crisis response pathway to prevent admission and placement breakdown 4)Development of a Specialist Autism Team working alongside existing teams on complex cases 5)Links with both MHLDA Provider Collaboratives who are leading on some of the identified priorities which sit under the overarching national LDA programme 6)Expansion of Forensic Outreach Liaison Services 7)Delivery of SY LDA Housing Needs Assessment 8)Implementation of the Care Education Treatment Review and Dynamic Support Register Policy to ensure that regular independent reviews are taking place to enable discharge planning and implement ICB assurance and escalation processes to provide overall assurance that we are meeting the policy requirements | Chris Edwards Rotherham Place Director | LDA Programme Risk | 3 | 4 | 9 | 12/12/2023 25/04/2024 15/07/2024 02/08/2024 28/10/2024 23/12/2024 07/02/2025 20/02/2025 07/04/2025 07/07/2025 17/07/2025 06/10/2025 | 2026-01-06 | Not overdue | Kelly Glover | July 25 - Safe Space site has been identified and offer is awaiting acceptance. Mobilised all age keyworking service and working with several adult inpatients to facilitate discharge as well as embedding a more preventative approach in the community. | Quarterly | ICB Place Committee | Quality Performance Patient Involvement Experience (QPPIE) | 45215 | 45200 | 524 | Update 17/7/25 - Not changed the risk ratings as whilst there has been progress with the mitigations, we will not see the benefit until later in the year and next year due to the mobilisation timeframe and the timeframes for discharge pathways being longer. Update 3/2/25 - Reduced the residual risk likelihood to 3 as there has been an updated trajectory to achieve of 10% less than baseline in April 24, this will be a challenge but is more achievable. All the same mitigations are in place with additional check ins for planned discharges in Q4 with all four places to ensure any issues/barriers are addressed promptly.
SY113 | ICB | Elective Care | 1 4 5 8 | BAF 1.6.1, BAF 1.6.3, BAF 2.9, BAF 2.10, BAF 2.12, BAF 2.13, BAF 2.14 | Waiting Times - There is a risk of failing to deliver the elective reform targets (referral to treatment (RTT) waiting time targets, and reducing the proportion of the RTT waiting list over 52 weeks to less than 1% of the total) due to high demand for services, workforce shortages, pandemic and industrial action backlogs, which may affect patient access, patient safety and experience, and SY ICB reputation. | 4 | 5 | 20 | Accountable | 1)Implement South Yorkshire and Bassetlaw Acute Federation (SYBAF) Diagnostic & Elective Recovery Plan 2)Getting It Right First Time (GIRFT) improvement programme 3)NHSE Quality Improvement support 4)Implement the 'choice' agenda for patients at the point of referral 5)Clinical improvement programmes in 6 fragile specialties 6)Paediatric innovator programme for children's specialties 7)Pathway reform, including referral criteria and Advice and Guidance with Primary & Secondary Care Interface Group | Sarah Perkins Director of Transformation and Delivery | Sarah Bayliss | 4 | 3 | 12 | 18/08/2023 11/09/2023 02/10/2023 11/10/2023 10/11/2023 15/12/2023 05/02/2024 18/03/2024 19/04/2024 24/07/2024 28/10/2024 04/11/2024 16/12/2024 20/12/2024 06/03/2025 09/06/2025 19/06/2025 22/09/2025 | 2025-12-22 | Not overdue | Cathy Hassell (Managing Director South Yorkshire & Bassetlaw Acute Federation) / Sarah Bayliss | June 2025 - As providers and systems have successfully reduced the volume of patients waiting over 65 weeks, the national focus has shifted to the constitutional standard of referral to treatment within 18 weeks. All providers are expected to deliver a 5% improvement on the Nov. 2024 baseline by the end of March 2026; this requires 4 of the 5 SYB Trusts to perform above the national target of 65%. The system is still struggling to recover waiting lists since COVID and industrial action. SYBAF Diagnostic and Elective Recovery Plans are in place. SYB providers are each working to implement OP and theatre improvement plans to increase productivity, supported by SYB collaborative working groups, GIRFT and NHSE Quality Improvement. SYB mutual aid principles and SOP agreed. Elective Oversight Group (EOG) members actively engaged to collaboratively improve RTT performance and reduce the proportion waiting over 52 weeks. Clinical improvement groups and the Primary & Secondary Care Interface Group are working on pathway reform including referral criteria and Advice and Guidance. Independent sector including insourcing and outsourcing utilised to supplement NHS capacity. | Quarterly | ICB Place Committee | Quality Performance Patient Involvement Experience (QPPIE) | 45156 | 45139 | 565 | Risk was discussed at the Acute Federation Board meeting which agreed that, given the current context, the post-mitigation score for the elective recovery risk can be raised to 16 (likelihood – 4 x impact x 4). They were reassured that the mitigation plan was robust but that industrial action had taken its toll, workforce challenges, UEC pressures and cases of high clinical urgency continue to threaten our ability to eliminate 65 week waits.
SY042 - R | All Places | Finance inc Fraud | 6, 7 | BAF 1.1.1 BAF 1.3, BAF 4.3 | Service Delivery - There is a risk that the number of transformation workstreams within Places are not delivered which will cause a non delivery of our plans of services population health improvement and potential funding gap. | 4 | 3 | 12 | Accountable | 1. Rotherham Place Committee receives updates at regular intervals- papers and verbal updates. 2. Rotherham Place Leadership Team meets weekly and can be a forum for any operational escalations . 3. The ICB via it's Improvement and Value Meetings (and in conjunction with central PMO) currently undertaking review of 500+ list ed transformation projects with a view to traiging and prioritising. This is a major mitigation . | Lee Outhwaite Chief Finance Officer | Previous CCG Risk Management Processes | 3 | 4 | 12 | 30/09/2024 04/11/2024 05/12/2024 30/01/2025 07/02/2025 05/06/2025 22/06/2025 30/07/2025 06/10/2025 | 2026-01-06 | not overdue | Wendy Allott Claire Smith | July 25 - high impact work is progressing with some successful outcomes in areas such as reducing respiratory admissions, although this is not improving the overall demand on attendances in UEC. Exec meetings with partners are in place with another scheduled for this month. updates through I&V October 2025 - ICB has met with TRFT colleagues twice now to progress work to look at how we reduce the bed base in acute through management of demand. A3 completed for this workstream | Monthly | ICB Place Committee | Finance & Investment Committee | 44900 | 44896 | 749 | Discussed at Finance and Investment Committee - identified matching BAF objective (4.3). Residual risk score increased to 5 x 4 = 20 14/10/24 - Split risks now applied on spreadsheet
SY040 - R | All Places | Children and Young People | 5, 6 | BAF 1.4.1, BAF 1.4.2, BAF 1.4.3.1, BAF 1.4.3, BAF 1.6.1, BAF 1.6.2, BAF 1.6.3 | Sustainability of Improvement in CAMHS Service Delivery (Neurodevelopmental Pathway) There is a risk of reduced sustainability of improvements in the quality of Child and Adolescent Mental Health Services (CAMHS), specifically within the neurodevelopmental pathway, due to long waits across the Integrated Care Board (ICB), with some areas having waits to access neurodevelopmental pathways up to 8 years. This may result in continued dissatisfaction with the service from GPs, families, and children and young people, as well as unmet needs leading to increased acuity in patient presentations | 3 | 4 | 12 | Accountable | Weekly meeting between RICB and RDaSH, CAMHS and TRFT. Monthly CAMHS contract performance meeting. " | Chris Edwards Rotherham Place Director | Previous CCG Risk Management Processes | 3 | 4 | 12 | 23/09/2024 23/12/2024 30/12/2024 01/04/2025 07/04/2025 30/06/2025 07/07/2025 06/10/2025 | 2026-01-06 | not overdue | Claire Smith | January 2025 - The peer review was superseded as we had an unannounced (CQC/OFSTED) inspection which went well and our outcome is now published. The positive outcome means we wont be inspected for at least 5 years. We have also agreed some non recurrent money for our CDC neurodevelopment assessment service to reduce waiting times (0-5 yrs) a trajectory is being developed with TRFT. funding transferred to trft and resource increasing to provide support to reduce waits - monitoring in place Oct 2025 - progressing well with additional resource in place | Quarterly | ICB Place Committee | Quality Performance Patient Involvement Experience (QPPIE) | 44900 | 44896 | 749 | 14/10/24 - Split risks now applied on spreadsheet
SY107 - R | All Places | Children and Young People | 1,2,3,4,5,6,7,8 | BAF 1.1, BAF 1.4.3.1, BAF 1.4.3, BAF 1.6.1, BAF 1.6.3 | Community Paediatrics/Childrens Pathways - There is a risk that current commissioned services, pathways and capacity of the services in place to support people are not aligned to meet the increasing needs of the Children and Young People (CYP) population (Including Autim Spectrum Disorder (ASD) Assessments, Sleep Pathways, Enuresis/Continence Support Speech and Language Therapy (SALT) and other related services is insufficient to meet the increasing demand resulting in people not receiving the timely care and support they require by the most appropriate service in the most appropriate setting. This could result in poor patient experience and impact upon quality of care and support. This also increases the risk that the ICB and Local Authority are unable to meet their statutory duties in relation to Education Health Care Plan (EHCP)/Special Eduacational Needs and Disaibilities (SEND) and means that children and young people are not having their needs met appropriately | 4 | 4 | 16 | Responsible | 1)ICB Place Committees/Leadership - oversight of risk and actions required to mitigate. 2)QPIE meetings 3)ICB operational executive 4)Place Governance in place for SEND, jointly with LA 5) CYP community services review agreed with TRFT July 25 | Katy Calvin-Thomas Barnsley Place Director | OE | 3 | 4 | 12 | 23/09/2024 23/12/2024 02/01/2025 01/04/2025 30/06/2025 06/10/2025 | 2026-01-06 | not overdue | Claire Smith | July 25 - high impact work is progressing with some successful outcomes in areas such as reducing respiratory admissions, although this is not improving the overall demand on attendances in UEC. Exec meetings with partners are in place with another scheduled for this month. updates through I&V. October 2025 - ICB has met with TRFT colleagues twice now to progress work to look at how we reduce the bed base in acute through management of demand. A3 completed for this workstream | Quarterly | ICB Place Committee | Quality Performance Patient Involvement Experience (QPPIE) | 45124 | 45108 | 589 | CQC and OFSTEAD inspection unannounced took place in October we have now had in public the outcome which is extremely positive. Inspectors expected in person week commencing 30th Sept. officers prepared well for this and have complied with all current requests for information, with a level of confidence in our ability to show the good work across our Place. We have also agreed through the SEND exec and Place Exec non recurrent funding for the CDC neurodevelopment assessments of 0-5 yr olds provided by the Trust. funding agreed March and transferred - increase in resource to support waiting list reduction commenced and being monitored
SY021 | ICB | Quality | 1,2,5,6,8 | BAF 1.1, BAF 1.6.1 | Learning Disability Mortality Review (LeDeR) - There is a risk that the ICB will not meet national policy requirements for LeDeR, this is due to delays in agreeing workforce and accountability framework, which may result in learning not being identified and embedded across the system to prevent avoidable deaths and reduce health inequalities. The ICB will also be in breach of Nationally set KPI's resulting in further action by NHSE | 4 | 3 | 12 | Responsible | 1) Development of a South Yorkshire Approach in line with the national policy Additional resource to address the backlog 2) Automation and streamlining processes Additional project management resource been allocated from central LDA team | Chris Edwards Rotherham Place Director | Previous CCG Risk Management Processes | 4 | 3 | 12 | 01/06/2022 07/12/2022 24/03/2023 30/03/2023 16/05/2023 06/06/2023 16/06/2023 06/07/2023 05/09/2023 16/10/2023 01/12/2023 10/01/2024 18/04/2024 29/07/2024 31/10/2024 03/02/2025 20/02/2025 07/04/2025 05/07/2025 06/10/2025 | 2026-01-06 | Not overdue | Kelly Glover / Anita Winter | 07/07/25 FTC LeDeR Reviewer extended to September 2025, the same concerns will apply regarding capacity when this post ends. In light of the planned new ICB model and given that there is uncertainty around the future of the LeDeR team contact with bereaved families for all Doncaster notifications has been placed on hold. A decision on how these will be progressed will be made once the outcome of the new model is clear. A new 'Rapid Review' process has been implemented for reviews aged 70+ The 'Rapid Review' which is a streamlined approach to ensure timely completion, efficient use of resources, and continued learning from deaths while maintaining the integrity of the LeDeR process. Progressing well with completing Rotherham backlog. 06/10/25 Rapid Review Process is offering some improvement. Reviewers have been set targets for completion of reviews per month based on their WTE to try to increase throughput. The number of notifications being received is increasing now to a daily basis. The FTC postholder has been extended to 31 March 2026 but a longer term capacity solution is still required. | Quarterly | ICB Place Committee | Quality Performance Patient Involvement Experience (QPPIE) | 44713 | 44713 | 882 | Residual likelihood reduced to 3 from 4 due to the ongoing development work and mitigations particularly due to making the fixed term post a permanent post which was due to finish in March 25.
SY082 - System | All Places | Mental Health Services inc. LD/Autism/CAMHS | 1,2,3,5,6 | BAF 1.4.1, BAF 1.6.3, BAF 2.9 | Adult Mental Health (MEED) - There is a risk of increased presentation of eating disorders in adults, across the ICB. . This is due to unmet need and lack of provision in this pathway across the system. Secondly there are issues around the current available services and the capacity of these to meet the needs of patients already known to services (all-age). Lastly, there is an increased need in the adult eating disorder pathway following Covid-19 and an exponential growth in the number of children and young people with eating disorders who are now transitioning to adult services. This is leading to increased acuity in presentations, increased demand on primary care, impact in acute hospital trusts (Medical Emergency in Eating Disorders [MEED] pathways) and increased demand on crisis provision and inpatient beds. | 3 | 4 | 12 | Accountable | 1)A partnership SY Eating Disorders programme, managed by the Provider Collaborative, is in place bringing together good practice, raising the profile of the need for improvements of services and collectively reviewing risks/priorities. 2)There is some commissioned provision with Sheffield Eating Disorders Service (SEDS) provided by SHSC for Sheffield, Barnsley and Rotherham. This is also accessed by some Doncaster patients via patient choice mechanisms. 3)There is a service for low to moderate support commissioned across South Yorkshire with SYEDA. 4)Support is provided to Acute Trusts from Mental Health Liaison Teams when patients are admitted with an eating disorder. MEED baseline work has been completed including current pathways and self-assessment of compliance. 5) investment identified to expand services in Barnsley, Doncaster and Rotherham has been confirmed. SHSC will be the lead provider for the service via their SEDs team and recruitment to the expansion posts is currently underway, with staff expected to start in the Autumn 2025. 6) MEED pathway work being jointly developed by Acute Federation and SY MHLDA Provider Collaborative. Plan to introduce a funded, co-ordinated service and oversight utilising 2025/26 funding. – New update: A paper was tabled at the Joint Committee for Eating Disorders on 11 August 2025 proposing to decommission a service called Stepping Stones that has been a pilot under specialised commissioning and reinvest the funds to implement a part year support proposal of: • 2 MEED workers • 2 PAs of a Consultant The cost would be £160,870 FYE or £67,055 for 25/26 PYE from November onwards, which is when recruitment could potentially be underway. 7) An EQIA on decommissioning the Stepping Stones service has been requested and an update is expected at the next meeting of the committee on 8 September 2025 7) Safe decomissioning of adult stepping stones service, with funding reallocated to support the recruitment of an adult MEED worker. | Chris Edwards Rotherham Place Director | Claire Smith following public complaints | 3 | 4 | 12 | 05/12/2022 24/03/2023 30/03/2023 19/04/2023 02/05/23 04/05/2023 16/05/2023 01/06/2023 03/07/2023 06/07/2023 01/08/2023 14/08/2023 04/09/2023 16/10/2023 01/11/2023 03/01/2024 08/01/2024 17/01/2024 01/02/2024 06/02/2024 01/03/2024 14/03/2024 15/04/2024 22/04/2024 29/07/2024 05/08/2024 16/09/2024 23/09/2024 26/09/2024 30/09/2024 01/11/2024 30/12/2024 03/02/2025 11/03/2025 07/04/2025 15/07/2025 18/08/2025 | 2025-11-18 | Not overdue | Sarah Boul | July 2025 The ICB and all NHS Provider Trusts have agreed to the establishment of the South Yorkshire Eating Disorders Joint Committee (SYEDJC), which has been running in shadow form since April, and has now been approved through all membership Boards. The SYEDJC agreed in July to progress with recruitment to the Barnsley, Doncaster and Rotherham eating disorders service expansion via SEDS (part of SHSC), but acknowledge that this service expansion will not fully address issues with ARFID, MEED or blood test capacity in primary care. These issues remain as a risk. In particular for MEED the proposal updated on in February 2025 to address issues has been paused due to there being no finance to support the proposals. Discussions are ongoing regarding this position. The SYEDJC also holds a risk register on these matters and this is updated monthly at committee meetings. September 2025 - An EQIA on decommissioning the Stepping Stones service was presented at the joint committee for eating disorders on 8 September 2025. It was agreed that the adult stepping stones service could be safely decommissioned, and the funding reallocated to support the recruitment of an adult MEED worker. It was not deemed safe to decommission the CYP Stepping Stones service and this will remain in place. | Quarterly | ICB Place Committee | Quality Performance Patient Involvement Experience (QPPIE) | 44900 | 44896 | 749 | Assessment of the balance of risk to be completed post outcome of discussions with MH Provider Collaborative. Sheffield: 07/08/24 - Corporate Risk Team met with WL. Action for IA to review score and provide update in conjunction with Sarah Boul
SY016 | ICB | Finance inc Fraud | 1,3,5,6 | BAF 1.3 | Fraud - There is a risk that Continuing Healthcare (CHC) / Personal Health Budget (PHB) funds provided for patient care are intentionally diverted by patients or their carers for other means not care related due to fraudulent activity resulting in loss of revenue for the ICB and lack of care for patients. | 3 | 4 | 12 | Responsible | 1)Robust policies for CHC and PHB. 2)Broadcare used where there are checks against costs. 3)PHBs are regularly audited 4)Where a risk may be evidence, advice would be requested from the Local Counter Fraud Officer. 5)All PHBs are signed and authorised 6) PHB are audited | Lee Outhwaite Chief Finance Officer | Previous CCG Risk Management Processes | 3 | 3 | 9 | 18/11/2022 02/03/2023 23/03/2023 19/04/2023 02/05/2023 16/05/2023 15/06/2023 06/07/2023 13/10/2023 01/11/2023 01/12/2023 03/01/2024 01/03/2024 22/07/2024 01/08/2024 09/09/2024 06/01/2025 06/02/2025 22/06/2025 30/07/2025 10/09/2025 | 2025-12-10 | Not overdue | Hayley Tingle (Leading on CHC Budget) | July 2025 - All four places: Audits undertaken identified specific risks in relation to PHB. Developing action plan in conjunction with Local Authority (LA) to ensure robust system and processes are in place to mitigate. This is part of our regular meetings with LA . Looking to bring this in house within the ICB as the finance function develops its roles. September 2025 , This continues to be on the CHC PID workplan for 25/26 although a refresh / review of the PID is currently taking place following the Model Blue Print for the ICB and where this function may sit in future , for assurance we continue to have regular audits for both in house and LA commissioned services to ensure no significant balances are built up by patients | Quarterly | ICB Place Committee | Audit and Risk Committee | 44883 | 44866 | 760 | no further updates , continue to explore in house option which takes the audit function away from LA . This is part of the CHC / Individual Placement PID which aims to ensure consistency of approach across the 4 places . The move away from LA will be part of this work . Meanwhile assurances and monitoring are obtained from LA to mitigate any risk of balances being accrued and action taken . 6/02/25 No further updates , this forms part of the PID work plan in 25/26
SY044 - R | All Places | Data | 1,5,6,8 | BAF 1.1.1, BAF 1.7, BAF 2.1, BAF 2,7,1, BAF 2.10, BAF 2.12, BAF 4.3 | Tackling Health Inequalities – the impact of the Covid-19 pandemic has been far reaching, and the social, economic and health impacts on each of our Place populations has created a challenge on health inequality and improving outcomes. Our system must be focussed on tackling health inequalities and ensuring we are informed by high quality data that is owned across partners for us to focus our priorities on areas of greatest need and impact for the population. | 5 | 5 | 25 | Accountable | 1) Established Integrated Care Partnership and agreed strategy - this is how we will work together as a system to reduce health inequalities. 2)Developing a joint NHS forward plan will have focus on how we work with others to reduce health inequalities in NHS. 3) 4 health and care place partnership plans developing in places have a focus on health inequalities working with Local Authorities, voluntary sector and others. 4) Integrated Care Board developed purpose and ambition one of the ambition is to tackle health inequalities. | Chris Edwards Rotherham Place Director | CCG Due Diligence Assurance Letters | 3 | 3 | 9 | 23/09/2024 30/12/2024 30/01/2025 01/04/2025 07/04/2025 30/06/2025 07/07/2025 | 2025-10-07 | 8 | Claire Smith | Through the recommissioning, there was a strong focus on making the service more holistic, sustainable, and considering wider outcomes, including mental health as part of the approach to measuring success. In January 2025 the h&WB chair facilitated a development session to support the refresh of the strategy, this included analysis of our health inequalities data and key areas for improvement across health outcomes. The strategy is expected to be refreshed in the first Q of 2025/26. Our Place Plan will also be refreshed in this timeline. Both will incorporate key priorities around health inequalities. We have also now launched (November 2024) the proactive care model - neighbourhood MDT working to support the prevention agenda. Refresh of Pop Health action plan at Place is underway with an event in May 25 to agree priorities, we have also had a Placed based neighbourhood working workshop in late June and are now moving forward with the maturity matrix to understand where we are against the national model and key next steps. discussion are also underway to understand how Place will continue to manage our Place Plan and board moving forward as the ICB changes in its model. | Quarterly | ICB Place Committee | Quality Performance Patient Involvement Experience (QPPIE) | 44900 | 44896 | 749 | Rotherham - Needs to be made more specific risk and linked to other health inequalities risks. Need to outline what outcomes we are not achieving. 5/12/24 - Confirmation from David Crichton that Place Directors accepted the ownership of the risk 23/12/2024 - Continue to strategically commission services ensuring that our populations needs including where we know we have health inequalities are considered. any decision to reduce, decommission or change services is accompanied by an equality impact assessment to ensure we understand the impact across a multitude of factors
SY061 | ICB | Primary Care | 2,5,6 | BAF 1.8, BAF 2.2, BAF 3.10 | Access to Primary Care Data - There is a risk that primary care related commissioning decisions are not evidence-based due to lack of knowledge/access to primary care data resulting in an inability to progress population health management and a risk of poorer outcomes for patients. | 3 | 3 | 9 | Accountable | 1)Population Health Management (PHM) and Risk stratification using Eclipse solution (Now in 93% of GPs across the ICB) 2)Communication and engagement with all Practices across the ICB is underway to get all practices to sign up to the ICB data sharing agreement. This will allow us to directly access primary care data. | Kieran Baker Chief Digital and Information Officer | Previous CCG Risk Management Processes | 2 | 2 | 4 | 05/12/2022 02/03/2023 19/04/2023 16/05/2023 06/07/2023 04/09/2023 16/10/2023 15/01/2024 15/04/2024 24/07/2024 28/10/2024 27/01/2025 05/02/2025 13/03/2025 01/08/2025 15/09/2025 | 2026-03-15 | Not overdue | Helen Stone / Barbara Coyle | September 2025 - Executive approval has also been granted to purchase a GP data feed from North East Commissioning Services Unit (NECS). Data Sharing Agreement (DSA) has been developed for practices to sign and commercials are being worked through with NECS. DPIAs have been drafted and communications to LMCs and practices has begun to get sign up to the use cases. 40 practices are signed up to share their data directly with the ICB and a new governance structure has been implemented to support decision-making regarding data sharing and linkage. 93% of all practices signed up to Eclipse. | Six Monthly | ICB Place Committee | Audit and Risk Committee | 44900 | 44896 | 749 | Barnsley suggested rewording to: There is a risk that data can not be captured across all sectors of health and care to support improved services delivery and transformation. This risk appears to be focussed upon GP's but actually there is probably an equal risk relating to all Primary Care Groups Rotherham Primary Care data is improving. Suggest close risk. 6/11/23 - Currently with V Lindon for review 13/12/23 - V Lindon unable to provide further update, feels would be better to be reviewed by Kieran and those noted as responsible for review
SY066 | ICB | Adult Services | 1,5,6 | BAF 2.13 | Delayed Discharge from Hospital both Acute and Mental Health - Impacting on Ambulance Handover delays, pressure in system compounded by Industrial Action (IA), capacity, workforce gaps both within and outside of acute care leading to the potential for deconditioning, further delays, avoidable harm and poor experience. Wrong place of care for optimum therapeutic treatment for people with mental health, Learning Disabilities and Autism (LDA) diagnosis. | 4 | 3 | 12 | Accountable | 1.Ongoing priority work as part of Urgent Emergency Care (UEC) alliance and priorities within each Place. 2. Creative workforce solutions being explored. Areas of good practice being shared via system executive leaders group. 3.Mental health Learning Disability and Autism (MHLDA) Programme 4. Monitoring of SI’s through quality forums 5. Ongoing Quality Improvement (QI) work with Emergency Care Improvement Support Team (ECIST) 6.Review of oversight across multiple mental commissioners planned. 7.System Efficiency Board convened across the ICS with focus on: Unfunded bed base / UEC demand to provide greater focus and visibility of ongoing UEC work at a place and/or system level and the likely impact on current provider unscheduled care / activity related cost pressures 8.Discharge pathways 9.Trusted Assessor models 10. Virtual Wards, and 11. escalation through ROC and TCG structures. | Dr David Crichton (Chief Medical Officer) | SQG - Regional Quality Group | 3 | 2 | 6 | 18/12/2022 02/03/2023 16/03/2023 16/05/2023 02/06/2023 06/07/2023 21/09/2023 16/10/2023 10/11/2023 09/01/2024 21/02/2024 27/05/2024 01/07/2024 01/10/2024 30/12/2024 14/04/2025 28/04/2025 | 2025-10-28 | Not overdue | Katie Roebuck-Marfleet | April 2025 - Risk of delayed discharge from acute and mental health hospitals, continuing to impact ambulance handover times and increase pressure across the system. Although industrial action has reduced, ongoing workforce gaps across acute, community, mental health, and social care sectors continue to affect flow. Patients are at ongoing risk of deconditioning, avoidable harm, and poor experience due to discharge delays. There remains a risk of patients with mental health needs, learning disabilities (LD) or autism (LDA) being placed in sub-optimal care settings, impacting recovery outcomes. | Six Monthly | ICB Place Committee | Quality Performance Patient Involvement Experience (QPPIE) | 44913 | 44896 | 739 | Work still ongoing
Formulas:
Next assessment due = VLOOKUP("*SY124*",'[1]10. Open Risks'!$A3:ZY4998,18,FALSE)
Next assessment due = VLOOKUP("*SY042 - R*",'[1]10. Open Risks'!$A3:ZY4998,18,FALSE)

## 14(iiI) Rotherham IL
Ref | Category | Place | Domain | Link to Board Assurance Framework | Risk Description | Likelihood | Impact | Score | RACI | Mitigation / Treatment | Lead risk owner | Source of Risk | Likelihood. | Impact | Residual Score | Date risk assessed | Person Responsible for Updates | Progress / Update | Date for reassessment | Assurance | Oversight | Date added to RR | Commentary to Support Review
[6 empty] | Initial Risk | Initial Risk | Initial Risk |  |  |  |  | Residual Risk
RPP001 | Mental Health Services **TO BE REMOVED FROM THE RISK REGISTER** | Rotherham | 1,2,5,6,8 | 1.2,2.1,2.2 | There is a risk that the reconfiguration of RDaSH Rehabilitation Pathways may increase demand for acute services through increased delays in the whole pathway (leading to a possible increase in OOA placements) | 3 | 4 | 12 | Accountable | RDASH to present to the Place Leadership Team (Nov 2023) evidence and service benefit/impact review of the decision to reconfigure rehabilitation pathways to decrease bed base whilst increasing community offer. Place partners to feedback and support in review of pathway design in order to mitigate risks across the to patients and partners | Claire Smith SYICB (Place Partnership) | Rotherham PET | 1 | 1 | 1 | 6.10.23 | Claire Smith Deputy Place Director (Rotherham) | Rdash informed SYICB colleagues of the decision to reconfigure pathways mid-sept, this was discussed at our PLT on 4th October with a request for RDASH to present to the group evidence and impact assurance for the model. This will be appriased by Place colleagues and support provided to ensure all risks are mitigated update 1/11/23. Risk reassessed as presentation and report submitted to PLT which has given further assurnace on impact. there will be 20% increase in community capcity with approach now over 7 days instead of 5. update 1/12/23 report to board discussed. monitoring imoact in coming weeks 22/12 update continue to monitor but low risk 1/3/24 - No further update on position work ongoing. April update - OOA placements are increasing but no evidence as yet linked will monitor and request an update at a Place Board in coming months. May Update - Julie Thornton will be presenting an update on Goldcrest closure and a review of any impact/actions taken to mitgate at Board this month. This may see this risk come off our register. June update: Julie Thornton presented a paper which highlighted the current position favourably, there doesnt seem to have been an impact due to the closure with additonal capacity being freed up to support in the community. The data analysis was only from a short period so risk remains for a further 3 mths until a more detail review takes place. OCT - as reported to PLT, since the change of pathway there has been 0 patients admitted to an out of area rehab bed and 0 concerns raised. Agreed this can be removed from the risk register. | 2023-12-01 | Monthly | Place Leadership Team
RPP004 | Financial posiiton and required savings/efficenies across Place | Rotherham | 1,2,3,4,5,6,7,8 |  | Financial Position across Place Partners - there is a risk that the significant financial challenge across Place Partners leads to organisational decisions on service delivery (including reduction or ceasing provision) that impact negative on Place Partners and the overall outcomes/health and weelbeing of the Rotherham populations | 4 | 5 | 20 | Accountable | Rotherham Place Leadership Board, refreshed Place Plan 23-25 with clear Place Priorities. Formal processes in place for escalation across partners in weekly PLT meetings. Finance executive leads meet regulalry with oversight at Board level. | Claire Smith SYICB (Place Partnership) Wendy Allott SYICB Chief Finance Officer | Rotherham Place Leadership Board & Rotherham Place Executive Team | 3 | 3 | 9 | 6.10.23 | Wendy Allott / Claire Smith | Discussion have taken place with partners through the PLT regarding working collaboratively on any MTFS plans. Shared understanding of financial positions has been discussed and continues to be an agenda item at Board. Commitment across Place to leave noone behind - in terms of understanding impact across Place partners of any decisions on savings/efficenies. Joint roles in place in commissioning that support integration across Place on decision making. 22/12 update our 4 transformational and efficency projects have been agreed at Place Board t&f groups will be established for these in new year and there will be updates for assurance to board as well as within ICB. work continues to ensure any decisions are shared across Place including Cuoncil sharing of there financial planning for 24-25 consultation out. 1/3/24 Finance is being taken through Place Board regualrly from Place partners collectively. PET: 06.03.24 - further review to take place April/May when there is better understanding of the financial regime for 24/25. May/June Update: Risk asssed and to remain as is. AUGUST UPDATE: 07/08/24 M3 ICB position went to FIC 02/08/24- awaiting feedback on any required actions/further impacts on Place. Leave risk as is for now. 29/08/24 Update from CE following exec/national meeting- ICB financial performance under national scrutiny / monitoring. Additional scruitiny on efficiency plans across the ICB/ICS in progress. October - Leave as is for now, November - no change, December No Change. March - 24-25 year end being worked through and a proposed financial allocation across providers is being worked up for 25 26, the plans have significant risk in terms of the savings identifed and there is also a remaining defifict of over 100m. APRIL - no further update. May - final allocations to budget holders including at Place are expected imminently, there has been agreement with NHSE to reach a balance plan but there is significant risk in achieving this. June - position remains as is July - No change work continues on demand management and efficencies within contracted services. Sept- the ICB is in turnaround due to the ongoing financial pressures, Rotherham Place team have supported the idenfication of in year non recurrent and recurrent savings to support the overall deficit position, any service changes have been through appropriate governance and EQIA. November - the Place team continue to review services to ensure VFM where appropriate and planning has commencd for 26 27 including development of commissioning intentions that brings spending in line with budgets. | Monthly | Monthly | Place Leadership Team
RPP006 | Infection Prevention and Control (IPC) Provision | Rotherham |  |  | There is a risk that Rotherham Place does not have sufficient resources in place to support Infection Prevention and Control initiatives across community settings. This may result in increased risk of infections within care settings and also a reduced ability to respond to incidents and emerging risk within the Rotherham Health and Care System. | 4 | 4 | 16 | Accountable | Discussions are underway across the Partnership to understand the potential options around resource. A paper describing the challenge, risks and options has been prepared by the Director of Public Health with support from the ICB. | Chris Edwards (Executive Place Director Rotherham) / Claire Smith SYICB (Place Partnership) & Andrew Russell Chief Nurse | Rotherham Place Leadership Board & Rotherham Place Executive Team | 2 | 3 | 6 | 2024-02-01 | Andrew Russell/Claire Smith | Options for non recurrent funding via IBCF is being discussed with a longer term solution required PET: 06.03.24 further work is taking place with the DPH to mitigate risk. April Update: Note 1 years funding has been secured and options are being worked up to reduce the risk based on that, but that there is no long term solution identified as yet to fund a Community IPC Service substantively. May/June Update - this remains an issue Rotherham is only LA in SY that doesnt have a resource for IPC, there has been a committment from BCF for one year but nothing recurrently which remains the concern. September update: Continued discussion with LA/TRFT with support from SY ICB in relatgion to achievable models with the 1 year funding (pilot provision for 12mths from IBCF funding.). No implememntation has yet been agreed. October, November, December - no further update. February - second joint SMT with RMBC which covers partnership working in financial context, supporting mitigation of the risks. Posiiton for 25 26 is being worked through as planning guidance has just been published March Update: Senior PH Practitioners began some work on CIPC, pulling together a Care Home IPC Champions group that now covers over 80% of Rotherham’s homes. That role has gradually transitioned into being 100% within the Health protection team with line management moving over and it will now predominantly focus on community IPC and undertaking proactive IPC audit work with homes as well as providing IPC support in outbreaks. The next step has been the identify funding for an IPC nurse to support the community work. Resource for a 0.5wte post will be available from September and work is taking place to find additional resource to make this a full time post. An update will be received at 2 April PLT. APRIL: Update received at PLT 2 April, options discussed but still work to do.May position is the same. June position remains the same. July Update: regarding the work of the Senior PH Practitioner to provide IPC support to care home - only 5 care homes remaining to be included within the IPC Champions network. Old person care home IPC audits: 23 carried out; with the remaining 16 to be completed by end of October. With respect to IPC Nurse capacity, the situation is currently as it was – recruitment to 0.5FTE expected in the Autumn, but additional funding opportunities are being explored to enhance this. | Monthly | Monthly | Place Leadership Team | 2024-02-01
RRP 0010 | Funding pay rise announcements | Rotherham | 1,2,3,4,5,6,7,8 |  | Pay settlements are being made with e.g. Junior doctors,consultants and further discussions are happening with all settings including social care and the voluntary sector. The risk is that these pay wards are not funded in all sectors | 4 | 3 | 12 | Accountable | Actions: Work with NHSE to understand funding streams to assess what is funded centrally and communicate risks to providers | Chris Edwards SYICB | Rotherham Place Board | 4 | 3 | 12 |  | Chris Edwards SYICB | September: Awaiting guidance from NHSE. November/December no update Feb Update: planning guidance just published and working through impact of this. March - settlement for collective action reach Nationally however, indications are that there will remain risks to ongoing provision of shared care/LES etc . APRIL: No further udpate. MAY - NO FURTHER UDPATE JUNE - NO FURTHER UDPATE. July Remains a risk but no confirmation of any further action planned. Sept - no change | Monthly | Monthly | Rotherham Place Board | 2024-08-28
RRP 0011 | Disproportionate impact for those experiencing health inequalities due to changes in the Maternity Tobacco Delivery Model within the Rotherham Maternity service | Rotherham |  |  | There is a risk that changes to the Maternity Tobacco Delivery Model within the Rotherham Maternity service will impact service uptake and outcomes and progress towards the national safety ambition to reduce still birth, neonatal mortality, maternal mortality and serious intrapartum brain injuries disproportionately on those experiencing adverse wider determinants of health including those from areas of highest deprivation. | 4 | 3 | 12 | Accountable | Reconfiguration of the Midwifery Service to continue to meet the NHS Long Term Plan commitments on smoking and health inequalities which include a smokefree pregnancy pathway. Further reducing demand for the service (due to the national success of the Public Health stop smoking campaign) and introduction of new innovations that have just commenced these include swap to stop ( Swapping smoking for a vape) and maternity incentives which rolls out in November incentivising women who choose to stop smoking. Although recommended, it is not a mandatory requirement to have a specialist midwife within the service providing training and support, the requirement is for appropriate clinical leadership. The specialist midwife (and TDA) should cease delivery of additional training/ coaching. Improve links between the midwifery service and the community service (connect) to provide additional support and resilience to the training offer (e.g. eLearning package via NCSCT) Reduced referrals, streamlined engagement requirement of incentive scheme and prioritisation of the offer of the minimum standard (max 4+6 face to face sessions) with TDA. (Cease delivery of additional sessions/ acceptance of re-referrals.) Develop a priority pathway to the community service for pregnant women and/ or partners who require support face to face TDA appointments beyond birth, including continued access to Nicotine Replacement Therapy (NRT) beyond birth. Develop a priority relapse prevention pathway (postnatally) with the community service. Permanently reconfigure the Community matron specification to link into pathway development work to improve feedback loop and ensure learning informs improved patient experience. The ICB meets monthly with the trust re contract performance and will monitor activity/impact | Claire Smith SYICB (Place Partnership) | Rotherham Place Board | 2 | 3 | 6 | 02.09.24 | Claire Smith SYICB (Place Partnership) / Alex Hawley (Director of Public Health, RMBC) | November Update: Partners are working collaboratvely to address the gaps and mitigate risk through reconfiguration of provision. Any risidual risk will be consider at this point. PLT have has a number of updates on progress and continue to be received. TRFT continue to express concern in the ending of the funding. December Update the same as November. Feb Update: Discussed at Jan board given expected TRFT impact, actions were taken between TRFT and BA to support undertsanding of community offer. ongoing monitoring of impact. March - no further update. March - no further update May - ICB met with TRFT to discuss residual risk, TRFT were to monitor impact internal (ICB monitoring through HI data analysis to Place Board) and provide feedback to RMBC/ICB if required on the gaps in provision June no known impact raised to date, this is being monitored. July TRFT have produced an impact assessment which is to be considered by RMBC Public Health. Sept this remains under review. November - trft continue to review the position and are in conversation with public health colleagues around opportunities to mitigate residual risks. | Monthly | Monthly | Rotherham Place Board | 02.09.24
RRP 0012 | Temporary Closure of Brambles | Rotherham | 1,2,3,4,5,6,7,8 |  | There is a risk that the unexpected temporary closure of Bramples older people's ward impacts on the ability to place Rotherham patients in our local beds creating OOA placements. | 4 | 4 | 16 | Accountable | Review through Place Board updates regularly, Increased monitoring of No criteria to reside in beds to improve flow and ensure Rotherham patients can be supported in Glades. Escalation through executives where delays occur. Brambles had to be temporary closed due to staffing pressures in late December, RDaSH communitcated well to ICB Place and partners and have taken a number of actions to prevent OOA placements. The Brambles unit is positioned in the same building as another bedded unit and both have not been fully utilised. RDaSH are trying to support all Rotherham Patients within the capacity at Glades. This is being monitored and to date there has been no OOA (out of Doncaster/NL) placement. Some patients have been placed in Doncaster and this is being monitored. The partners are also supporting with ensuring flow through beds in a timely manner | Andre Brankin | Rotherham Place Board | 2 | 3 | 6 | 06.02.25 | Andrew Brankin | Brambles had to be temporary closed due to staffing pressures in late December, RDaSH communitcated well to ICB Place and partners and have taken a number of actions to prevent OOA placements. The Brambles unit is positioned in the same building as another bedded unit and both have not been fully utilised. RDaSH are trying to support all Rotherham Patients within the capacity at Glades. This is being monitored and to date there has been no OOA (out of Doncaster/NL) placement. Some patients have been placed in Doncaster and this is being monitored. The partners are also supporting with ensuring flow through beds in a timely manner March - no further update. APRIL: RDASH are to share that paper on proposals with partners - agreement on which meeting this will go to by CE and TL. MAY - NO FURTHER UDPATE. June - TL attended the place board in may to discuss the RDASH Board decision and next steps. agreed that ICB and partners would meet to look at how worked collaboratively to shape the model for investment into community July Update ICB met with RMBC and RDASH to discuss community offer and engagement with partners on pathways. RDASH are pulling together options which will be shared with partners for comment in terms of next steps No Older Adults have been placed out of area since the closure on 31st December 2024. In January – May 2025 there were 14 older adults cared for elsewhere in the RDaSH footprint, in the same timescale (5 months) prior to the closure there were 15. | Monthly | Monthly | Rotherham Place Board | 2025-01-01
RRP 0014 **NEW** | Healthwatch Risk | Rotherham | 1,2,3,4,5,6,7,8 |  | If central government amends the Health & Social Care Act to remove Healthwatch’s statutory obligations, Healthwatch Rotherham (HWR) may be abolished and its core functions (independent community engagement, local intelligence gathering, and scrutiny) transferred directly to the Integrated Care Board (ICB) and Rotherham Metropolitan Borough Council (RMBC). This legislative change could force the closure of HWR, interrupt ongoing projects and community feedback loops, weaken independent challenge in health and social care decision-making, and place existing staff at high risk of redundancy. | 4 | 3 | 12 | Accountable | This will be an identified risk across SYICB and as such is escalated internally, Rotherham Place including both the ICB and Council will continue to support Healthwatch as a valued partner as clarity emerges nationally on the proposed model. At a local level there is acknowledgement of the positive role played by Healthwatch in our partnership. | Kym Gleeson | Rotherham Place Board | 4 | 3 | 12 | 08.10.25 | Kym Gleeson | no further detail has emerged from central government, SYICB and Place partners continue to await further clarity prioir to understanding any local decisions that may need to be made. | Monthly | Monthly | Rotherham Place Board | 2025-10-01

## 20. Rotherham Place Partnership
Ref | Category | Place | Domain | Link to Board Assurance Framework | Risk Description | Likelihood | Impact | Score | RACI | Mitigation / Treatment | Lead risk owner | Source of Risk | Likelihood. | Impact | Residual Score | Date risk assessed | Person Responsible for Updates | Progress / Update | Date for reassessment | Assurance | Oversight | Date added to RR | Commentary to Support Review
[6 empty] | Initial Risk | Initial Risk | Initial Risk |  |  |  |  | Residual Risk
RPP001 | Mental Health Services **TO BE REMOVED FROM THE RISK REGISTER** | Rotherham | 1,2,5,6,8 | 1.2,2.1,2.2 | There is a risk that the reconfiguration of RDaSH Rehabilitation Pathways may increase demand for acute services through increased delays in the whole pathway (leading to a possible increase in OOA placements) | 3 | 4 | 12 | Accountable | RDASH to present to the Place Leadership Team (Nov 2023) evidence and service benefit/impact review of the decision to reconfigure rehabilitation pathways to decrease bed base whilst increasing community offer. Place partners to feedback and support in review of pathway design in order to mitigate risks across the to patients and partners | Claire Smith SYICB (Place Partnership) | Rotherham PET | 1 | 1 | 1 | 6.10.23 | Claire Smith Deputy Place Director (Rotherham) | Rdash informed SYICB colleagues of the decision to reconfigure pathways mid-sept, this was discussed at our PLT on 4th October with a request for RDASH to present to the group evidence and impact assurance for the model. This will be appriased by Place colleagues and support provided to ensure all risks are mitigated update 1/11/23. Risk reassessed as presentation and report submitted to PLT which has given further assurnace on impact. there will be 20% increase in community capcity with approach now over 7 days instead of 5. update 1/12/23 report to board discussed. monitoring imoact in coming weeks 22/12 update continue to monitor but low risk 1/3/24 - No further update on position work ongoing. April update - OOA placements are increasing but no evidence as yet linked will monitor and request an update at a Place Board in coming months. May Update - Julie Thornton will be presenting an update on Goldcrest closure and a review of any impact/actions taken to mitgate at Board this month. This may see this risk come off our register. June update: Julie Thornton presented a paper which highlighted the current position favourably, there doesnt seem to have been an impact due to the closure with additonal capacity being freed up to support in the community. The data analysis was only from a short period so risk remains for a further 3 mths until a more detail review takes place. OCT - as reported to PLT, since the change of pathway there has been 0 patients admitted to an out of area rehab bed and 0 concerns raised. Agreed this can be removed from the risk register. | 2023-12-01 | Monthly | Place Leadership Team
RPP002 | Diabetes Pathway | Rotherham | 1,2,5,6,8 |  | There is a risk that patients with diabetes in Rotherham are not managed effectively or equitably leading to additional pressure on primary and secondary care services. | 4 | 4 | 16 | Accountable | There has been ongoing work to try and support better pathways in primary and secondary care - this has been difficult to effect change and more recently a paper was taken to our PET to agree additonal short term (2yr) funding of resource across place to lead transformation. There is a T&F group establish and once in post this resource will drive our key priorities which have alreayd been identified and are part of our PLACE priorities and agreed with TRFT | Claire Smith SYICB (Place Partnership) | Rotherham PET | 2 | 2 | 4 | 2023-11-01 | Claire Smith Deputy Place Director (Rotherham) Stuart Lakin (Rotherham) | Post agreed, will sit with TRFT but will be a transformational role for Place. T&F group established and work underway to recruit. Update 1/12/23. recuritment underway, this is now agreed Place priority linked to our 4 key areas of transformation on QSIR methodology for 24-25. Project checklist completed and prescribing savings identified (inital thoughts only). 22.12 update recruitment underway for the project lead 1/3/24 post appointed to workshop by March 21st with presentation to exec board on progress and proposed next steps. April update - new starter commenced and work is starting to progress request to close risk at next board May/June update - work is ongoing established T&F and awaiting baseline, expected outcomes to monitor in support of transformation. A regular oversight group meets within ICB to monitor progress and feeds into Board for assurance. August - high impact work in progress, outcome measures agreed and working through finanical impact of implementing transformation. September remains as is. October work progressing with financial impact being measured and clear timelines for completion to take to Board in coming months. Same position in November report to PET 31st October Same position in December. | Monthly | mn, | Place Leadership Team
RPP003 | Mental Health Services inc. LD/Autism/ CAMHS | Rotherham | 1,2,5,6,8 |  | Trauma Resilience Service - There is a risk of funding being unavailable from March 2025 onwards. Previous funding was received from Health and Justice since 2017/18 to support the Rotherham response to the findings of the Alexis Jay report in 2014. If external funding ceases there is a risk to the longevity of the service leaving a reduced service offer to those who have suffered exploitation. This could also result in adverse media attention . The Stovewood investigation into non recent child sexual exploitation is expected to continue for a number of years | 4 | 4 | 16 | Accountable | Review of mental health services commissioned by Rotherham ICB to understand demand and value for money in current model. Working with TRS to horizon scan and support to apply for external funding where available. | Chris Edwards (Executive Place Director Rotherham) | Rotherham Place Executive Team | 2 | 2 | 4 | 30/06/2023 11/08/2023 | Andrew Russell / Claire Smith | No funding expected from Health and Justice, Rotherham Place ICB has funding identified to March 2025 however, with a significant defict planned for next finacial year funding of the model is unsustainable past this point. A full review of the outcomes of the service, funding for this cohort across our Place partners and required demand/model moving forward is required and will commence shortly. initial conversations have taken place to raise this risk with the provider and a meeting will disucss further in October. Risk to be tolerated. Review continues. Risk to be tolerated. Review continues. 1/3/24 review completed and report presented to PET, national funding of 350K is being proposed to support a SY model with the provider, H&J Rotherham funding is proposed to be provided over 2yrs to support a transition into the new SY model which will mitigate risk of loss of this element of funding in March 25. Business case by RDASH completed and sent to H&J. April update - currently lobbying Home Office for specific funding to ensure all court cases are supoprted to 2026, funding for SY model has been conformed May/June update - position remains awaiting home office July Update: Janine Cherry- Swaine submitted a business case for funding for 24/25 onwards, the draft business case some clarifications. required, once received a central finance business case for the funding will be developed. Sept - still awaiting update from Home Office. October positive news regarding funding of a rotherham specific service to be incorporated into the RDASH SY model. Still awaiting detail to assess if the risk can be withdrawn. November - proposal submitted to RDASH awaiting response. December Update: RDASH Execs have approved funding to extend the voluntary sector input during 2026/27, the technicalities are being worked through. This risk to be removed. | Six Monthly | Rotherham Place Executive Meeting / Stovewood Strategic Coordination Group | Quality, Performance, Involvement, Experience | 2023-06-30 | Risk to be removed.
RPP004 | Financial posiiton and required savings/efficenies across Place | Rotherham | 1,2,3,4,5,6,7,8 |  | Financial Position across Place Partners - there is a risk that the significant financial challenge across Place Partners leads to organisational decisions on service delivery (including reduction or ceasing provision) that impact negative on Place Partners and the overall outcomes/health and weelbeing of the Rotherham populations | 4 | 5 | 20 | Accountable | Rotherham Place Leadership Board, refreshed Place Plan 23-25 with clear Place Priorities. Formal processes in place for escalation across partners in weekly PLT meetings. Finance executive leads meet regulalry with oversight at Board level. | Claire Smith SYICB (Place Partnership) Wendy Allott SYICB Chief Finance Officer | Rotherham Place Leadership Board & Rotherham Place Executive Team | 3 | 3 | 9 | 6.10.23 | Wendy Allott / Claire Smith | Discussion have taken place with partners through the PLT regarding working collaboratively on any MTFS plans. Shared understanding of financial positions has been discussed and continues to be an agenda item at Board. Commitment across Place to leave noone behind - in terms of understanding impact across Place partners of any decisions on savings/efficenies. Joint roles in place in commissioning that support integration across Place on decision making. 22/12 update our 4 transformational and efficency projects have been agreed at Place Board t&f groups will be established for these in new year and there will be updates for assurance to board as well as within ICB. work continues to ensure any decisions are shared across Place including Cuoncil sharing of there financial planning for 24-25 consultation out. 1/3/24 Finance is being taken through Place Board regualrly from Place partners collectively. PET: 06.03.24 - further review to take place April/May when there is better understanding of the financial regime for 24/25. May/June Update: Risk asssed and to remain as is. AUGUST UPDATE: 07/08/24 M3 ICB position went to FIC 02/08/24- awaiting feedback on any required actions/further impacts on Place. Leave risk as is for now. 29/08/24 Update from CE following exec/national meeting- ICB financial performance under national scrutiny / monitoring. Additional scruitiny on efficiency plans across the ICB/ICS in progress. October - Leave as is for now, November - no change, December No Change | Monthly | Monthly | Place Leadership Team
RPP005 | Mental health review (RMBC lead) | Rotherham | 1,2,3,4,5,6,7,8 |  | There are both financial & capacity (including clinical capacity) risks across Place partners related to the proposed changes to the Mental health pathways for adult social care, there is also a risk of impact to patients outcomes if the transition isnt managed appropriately across partners | 4 | 4 | 16 | Accountable | Rotherham Place Leadership team took a presentation on the proposed changes and impact, reports going through RMBC governance to Cabinet in Dec 23 and through partners governance, There is a commitment across partners to minimise impact and to ensure that the transition is phased to support the ability of Place to deal with the proposed changes collaboratively | Claire Smith SYICB (Place Partnership) Kirsty Littlewood AD RMBC Julie Thornton RDASH | Rotherham Place Leadership Board & Rotherham Place Executive Team | 2 | 2 | 4 | 1.11.23 | Claire Smith Deputy Place Director (Rotherham) / Kirsty Littlewood AD RMBC | Discussions have taken place with partners through the PLT regarding working collaboratively with weekly meetings now set up across partners. Working group has been established and workshops taking Place with all partners, includes engagement with patients/carers. Shared understanding of impact has been discussed with interim offers agreed past March 24 to support transition. Cabinet approval is required in December and significant flexibility will be built into implementation to ensure safe provision. Update KL - 5/2 cabinet approved working through impact with updates to Place board / JTh - RDASH will present a detailed risk review during February 2024. May Update: suggestion that this is reduced to 2 and 2, however RMBC need to confirm agreement of this, will be confirmed in the next update.JUNE - residual risk reduced to '2 x 2'scoring, proposed by CS and approved by KL. AUGUST UPDATE: IN AGREEMENT WITH J THORNTON, K LITTLEWOOD AND C SMITH THIS RISK IS TO BE STOOD DOWN - IMPACT HAS NOT BEENT TO THE LEVEL EXPECTED | Monthly | Monthly | Place Leadership Team | 2023-11-01
RPP006 | Infection Prevention and Control (IPC) Provision | Rotherham |  |  | There is a risk that Rotherham Place does not have sufficient resources in place to support Infection Prevention and Control initiatives across community settings. This may result in increased risk of infections within care settings and also a reduced ability to respond to incidents and emerging risk within the Rotherham Health and Care System. | 4 | 4 | 16 | Accountable | Discussions are underway across the Partnership to understand the potential options around resource. A paper describing the challenge, risks and options has been prepared by the Director of Public Health with support from the ICB. | Chris Edwards (Executive Place Director Rotherham) / Claire Smith SYICB (Place Partnership) & Andrew Russell Chief Nurse | Rotherham Place Leadership Board & Rotherham Place Executive Team | 3 | 3 | 9 | 2024-02-01 | Andrew Russell/Claire Smith | Options for non recurrent funding via IBCF is being discussed with a longer term solution required PET: 06.03.24 further work is taking place with the DPH to mitigate risk. April Update: Note 1 years funding has been secured and options are being worked up to reduce the risk based on that, but that there is no long term solution identified as yet to fund a Community IPC Service substantively. May/June Update - this remains an issue Rotherham is only LA in SY that doesnt have a resource for IPC, there has been a committment from BCF for one year but nothing recurrently which remains the concern. September update: Continued discussion with LA/TRFT with support from SY ICB in relatgion to achievable models with the 1 year funding (pilot provision for 12mths from IBCF funding.). No implememntation has yet been agreed. October, November, December - no further update | Monthly | Monthly | Place Leadership Team | 2024-02-01
RPP 008 (NEW) | MHRA bed alert | Rotherham | 1,3,5,6,8 |  | There is a risk of injury or death from entrapment or falls from medical beds, trolleys, bed rails, bed grab handles and lateral turning devices, as alerted by the medicines and healthcare product regulatory agency. | 2 | 4 | 8 | Accountable | Each impacted organisation in Rotherham to complete and maintain mitigating actions stated by the MSRA. These are to risk assess all patients who are using this equipment, prioritising those with atypical anatomy and updating when clinical conditions change; update policies and procedures; develop and implement a training plan; review medical device management systems; implement maintenance and servicing schedules; | Mediquip: Community Occupational Therapy: Kirsty Littlewood/Jodie Roberts Hospice: Mat Cottle Shaw TRFT Therapy and nursing: Jodie Roberts Care Homes: Owners/Directors | Rotherham Place Leadership Team | 2 | 3 | 6 | 2024-05-28 | Claire Smith | RDaSH and TRFT have set up working groups and Mediquip and the Hospice have action plans SY ICB commissioning team are co-ordinating assurance of the mitigating actions including circulating the alert twice to care homes and issuing and reviewing an audit quetionnaire to establish the number of impacted residents, actions and timeline and outstanding actions June update - paper presented to Place Board in May 24 a further update exepcted in 3 mths. July - further paper with updated action plan to Place Leadership this week 3rd July. Sept - process agreed at PLT regarding assessments to ensure consistency across partners, risk remains due to number of people still awaiting review. regular updates to PLT in place and within providers. October futher update scheduled for PLT this month no known escalations at this point. No further updates in November or Decemer position remains | Monthly | Monthly | Place Leadership Team | 01 06 24
RRP 0010 (NEW) | Funding pay rise announcements | Rotherham | 1,2,3,4,5,6,7,8 |  | Pay settlements are being made with e.g. Junior doctors,consultants and further discussions are happening with all settings including social care and the voluntary sector. The risk is that these pay wards are not funded in all sectors | 4 | 3 | 12 | Accountable | Actions: Work with NHSE to understand funding streams to assess what is funded centrally and communicate risks to providers | Chris Edwards SYICB | Rotherham Place Board | 4 | 3 | 12 |  | Chris Edwards SYICB | September: Awaiting guidance from NHSE. November/December no update | Monthly | Monthly | Rotherham Place Board | 2024-08-28
RRP 0011 (NEW) | Disproportionate impact for those experiencing health inequalities due to changes in the Maternity Tobacco Delivery Model within the Rotherham Maternity service | Rotherham |  |  | There is a risk that changes to the Maternity Tobacco Delivery Model within the Rotherham Maternity service will impact service uptake and outcomes and progress towards the national safety ambition to reduce still birth, neonatal mortality, maternal mortality and serious intrapartum brain injuries disproportionately on those experiencing adverse wider determinants of health including those from areas of highest deprivation. | 4 | 3 | 12 | Accountable | Reconfiguration of the Midwifery Service to continue to meet the NHS Long Term Plan commitments on smoking and health inequalities which include a smokefree pregnancy pathway. Further reducing demand for the service (due to the national success of the Public Health stop smoking campaign) and introduction of new innovations that have just commenced these include swap to stop ( Swapping smoking for a vape) and maternity incentives which rolls out in November incentivising women who choose to stop smoking. Although recommended, it is not a mandatory requirement to have a specialist midwife within the service providing training and support, the requirement is for appropriate clinical leadership. The specialist midwife (and TDA) should cease delivery of additional training/ coaching. Improve links between the midwifery service and the community service (connect) to provide additional support and resilience to the training offer (e.g. eLearning package via NCSCT) Reduced referrals, streamlined engagement requirement of incentive scheme and prioritisation of the offer of the minimum standard (max 4+6 face to face sessions) with TDA. (Cease delivery of additional sessions/ acceptance of re-referrals.) Develop a priority pathway to the community service for pregnant women and/ or partners who require support face to face TDA appointments beyond birth, including continued access to Nicotine Replacement Therapy (NRT) beyond birth. Develop a priority relapse prevention pathway (postnatally) with the community service. Permanently reconfigure the Community matron specification to link into pathway development work to improve feedback loop and ensure learning informs improved patient experience. The ICB meets monthly with the trust re contract performance and will monitor activity/impact | Claire Smith SYICB (Place Partnership) | Rotherham Place Board | 2 | 3 | 6 | 02.09.24 | Claire Smith SYICB (Place Partnership) / Ben Anderson (Director of Public Health, RMBC) | November Update: Partners are working collaboratvely to address the gaps and mitigate risk through reconfiguration of provision. Any risidual risk will be consider at this point. PLT have has a number of updates on progress and continue to be received. TRFT continue to express concern in the ending of the funding. December Update the same as November. | Monthly | Monthly | Rotherham Place Board | 02.09.24